## Sheet1 (hidden)
TTL PROGRAM
SECTOR WORKPLAN 2016 - 2018
ACTIVITY | SUB ACTIVITY/ PROCESS | BARANGAY | Remaining Target | TARGET UNIT | labost cost/ unit | Notes | FY17-Q3 |  |  | FY17 - Q4 |  |  | FY18 - Q1 |  |  | FY18 - Q2
[7 empty] | JAN | FEB | MAR | APRL | MAY | JUNE | JUL | AUG | SEP | OCT | NOV | DEC
M&E
Development of comprehensive monitoring system | Project LogFrame Creation and Review | N/A
| Project M&E Plan Creation and Review | N/A
| Review, Finalize, and Socialize Monitoring Tools - Shelter | N/A
| Review, Finalize, and Socialize Monitoring Tools - WatSan | N/A
| Review, Finalize, and Socialize Monitoring Tools - Livelihoods | N/A
| Review, Finalize, and Socialize Monitoring Tools - Health | N/A
| Review, Finalize, and Socialize Monitoring Tools - DRR | N/A
| Data Audit and Data Quality Assessment | N/A
| Field Observation | N/A
| Review and Revise Annual Targets | N/A
| Monthly Delegation Report Sectoral Meetings | N/A
| Monthly Delegation Report Composition | N/A
| Quarterly Report Composition | N/A
Development of outcomes measurement system | Endline Study Execution | N/A
| Final Project Evaluation | N/A
Promotion of participatory M&E methods | Community Orientation - Participatory M&E | N/A
| Semi Annual PME Meeting (Community Vision Mapping, CAP Updating, Workplan) | N/A
Development of management information system | Project Database Table Maintenance | N/A
| Project Database Frontend Developed | N/A
| Project Server Developed | N/A
| Project Server Maintenance | N/A
Development of comprehensive accountability system | Review and Finalize Accountability Framework | N/A
| Review and Finalize Accountability Plan | N/A
| Operationalize Accountability Framework | N/A
| Feedback Mechanism Operationalization - Paper-Based Feedback Forms | N/A
| Feedback Mechanism Operationalization - SMS-Based Feedback Forms | N/A
| Monthly Accountability Report Composition | N/A
Capacity building of PRC staff and volunteers on key M&E technical abilities | Content Development and Training Facilitation - Project Management Concepts | N/A
| Content Development and Training Facilitation - Quantitative Data Analysis Concepts (Excel, R) | N/A
| Content Development and Training Facilitation - Qualitative Data Analysis Concepts (Excel, R) | N/A
Collection and documentation of lessons learned | Data Analysis and Presentation - STED Study | N/A
| Data Analysis and Presentation - CBHFA Study | N/A
| Data Analysis and Presentation - CHAST Study | N/A
| QPR Reflection Meeting | N/A
| Internal Program Review | N/A
| Brownbag Implementation | N/A
| Consolidation of Learning Package | N/A
Promotion of strategic communications | Success Story Compilation | N/A
| MSC Video Collection | N/A
| Photo Collection | N/A
| Program Mapping Support | N/A
| Program TV Content Development | N/A
| IEC Materials Special Projects | N/A

## Unit Workplan
Task | FY2017 |  |  |  | FY2018 | [5 empty] | Responsible | Accountable | Consulted | Informed | Notes
| Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  | Accountable | Consulted | Informed | Informed
Development of comprehensive monitoring system (Will)
LogFrame and M&E Plan
Project LogFrame Creation and Review | [10 empty] | Karen | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Mar to FY2017 Apr
Project M&E Plan Creation and Review | [10 empty] | Karen | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Mar to FY2017 Apr
Monitoring Tools
Review Monitoring Tools - Shelter - SRA Top-Up | [10 empty] | Grace | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 May to FY2017 Jun
Review Monitoring Tools - WatSan - SRA Latrines | [10 empty] | Grace | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Mar to FY2017 Apr
Review Monitoring Tools - Livelihoods - CB STED | [10 empty] | Grace | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Apr
Review Monitoring Tools - Livelihoods - Enterprise Development | [10 empty] | Grace | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Apr
Review Monitoring Tools - Livelihoods - CMLP | [10 empty] | Will | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Mar to FY2017 Apr
Review Monitoring Tools - Health - CBHFA | [10 empty] | Will | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Mar
Review Monitoring Tools - DRR - Contingency Planning | [10 empty] | Grace | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 Apr to FY2017 May
Review Monitoring Tools - DRR - DRR in Schools | [10 empty] | Grace | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 May to FY2017 Jun
Reporting
Monthly Delegation Report ITT Construction | [10 empty] | Karen | Will | Will, Sector Heads | Will
Monthly Delegation Report Composition | [10 empty] | Jake | Matt | Will, Sector Heads | Margaret, Matt, Chris
Quarterly Report ITT Construction | [10 empty] | Karen | Will | Will, Sector Heads | Will
Quarterly Report Composition | [10 empty] | Will | Will | Will, Sector Heads, Matt | Margaret, Matt, Chris, Brian | bar: FY2017 Apr; FY2018 Jul; FY2018 Oct
Data Quality
Data Quality Assessment | [10 empty] | Karen, Will | Will | Will, Sector Heads | Matt, Margaret, Friday, Bryan, Sector Heads | bar: FY2017 May; FY2018 Oct
Development of outcomes measurement system (Will)
Endline Survey
Endline Study TOR Development | [10 empty] | Will | Will | Margaret, Ranjan, Matt, Sector Heads | Margaret, Matt | bar: FY2017 May to FY2017 Jun
Endline Study TOR Posting | [10 empty] | Will | Will | Margaret, Matt | Margaret, Ranjan, Matt, PMER Network | bar: FY2018 Jul
Endline Study Consultant Selection | [10 empty] | Will | Will | Margaret, Ranjan, Matt | Margaret, Ranjan, Matt | bar: FY2018 Aug
Endline Study Execution | [10 empty] | Consultant, Will | Will | Margaret, Matt, Sector Heads | Margaret, Matt | bar: FY2018 Sep to FY2018 Oct
Endline Study Report Drafting | [10 empty] | Consultant | Will | Margaret, Matt, Sector Heads | Margaret, Matt, Sector Heads | bar: FY2018 Oct
Endline Study Report Review | [10 empty] | Will | Will | Margaret, Matt, Sector Heads | Margaret, Matt, Sector Heads | bar: FY2018 Oct
Final Project Evaluation
Final Project Evaluation TOR Development | [10 empty] | Will | Will | Margaret, Ranjan, Matt | Margaret, Ranjan, Matt | bar: FY2017 Jun to FY2018 Jul
Final Project Evaluation TOR Posting | [10 empty] | Will | Will | Margaret, Ranjan, Matt | Margaret, Ranjan, Matt, PMER Network | bar: FY2018 Aug to FY2018 Sep
Final Project Evaluation Consultant Selection | [10 empty] | Will | Will | Margaret, Ranjan, Matt | Margaret, Ranjan, Matt | bar: FY2018 Oct
Final Project Evaluation Execution | [10 empty] | Consultant, Will | Will | Margaret, Matt, Sector Heads | Margaret, Matt, Sector Heads | bar: FY2018 Nov to FY2018 Dec
Final Project Evaluation Report Drafting | [10 empty] | Consultant | Will | Margaret, Matt, Sector Heads | Margaret, Matt, Sector Heads | bar: FY2018 Dec
Final Project Evaluation Report Review | [10 empty] | Will | Will | Margaret, Matt, Sector Heads | Margaret, Matt, Sector Heads | bar: FY2018 Dec
Promotion of participatory M&E methods (Grace)
Refresher Course on PME facilitation - Community Vision Map Review | [10 empty] | Grace | Grace | Will, COs, Matt | Will, COs, Matt, Aaron, Steve | bar: FY2018 Sep
Refresher Course on PME facilitation - CAP Review | [10 empty] | Grace | Grace | Will, COs, Matt | Will, COs, Matt, Aaron, Steve | bar: FY2018 Sep
Refresher Course on PME facilitation - Community Workplan Review | [10 empty] | Grace | Grace | Will, COs, Matt | Will, COs, Matt, Aaron, Steve | bar: FY2018 Sep
Semi Annual PME Meeting - Community Vision Map Review | [10 empty] | Community PME Volunteers, Dina, Edna, Ailene, Grace | Grace | Will | Will, COs, Matt, Aaron, Steve | bar: FY2018 Sep
Semi Annual PME Meeting - CAP Review | [10 empty] | Community PME Volunteers, Dina, Edna, Ailene, Grace | Grace | Will | Will, COs, Matt, Aaron, Steve | bar: FY2018 Sep
Semi Annual PME Meeting - Community Workplan Review | [10 empty] | Community PME Volunteers, Dina, Edna, Ailene, Grace | Grace | Will | Will, COs, Matt, Aaron, Steve | bar: FY2018 Sep
Procurement for printing of outputs | [10 empty] | Program admin | Grace | Will | Will | bar: FY2018 Sep to FY2018 Nov
Printing of activity outputs | [10 empty] | Dina, Edna, Ailene | Grace | Will | Will, COs, Matt, Aaron, Steve | bar: FY2018 Nov
Development of management information system (Karen)
Webviz Maintenance and Development
Revisions to Hardware Indicators Page | [10 empty] | Karen | Karen | Will, Daniel, Matt | Will, Matt, Margaret, Sector Heads | bar: FY2017 Apr
Revisions to Software Indicators Page | [10 empty] | Karen | Karen | Will, Daniel, Matt | Will, Matt, Margaret, Sector Heads | bar: FY2017 Apr
Revisions to Shelter-Core Intervention Page | [10 empty] | Karen | Karen | Will, Daniel, Aaron | Will, Matt, Margaret, Sector Heads | bar: FY2017 May
Revisions to Livelihood-STED Intervention Page | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will, Matt, Margaret, Sector Heads | bar: FY2017 Apr
Revisions to Livelihood-Agriculture Extension Intervention Page | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will, Matt, Margaret, Sector Heads | bar: FY2017 Mar to FY2017 Apr
Revisions to Household Overview Page | [10 empty] | Karen | Karen | Will, Daniel, Matt | Will, Matt, Margaret, Sector Heads | bar: FY2017 Mar
Revisions to Community Overview Page | [10 empty] | Karen | Karen | Will, Daniel, Matt | Will, Matt, Margaret, Sector Heads | bar: FY2017 Mar
Backend Overhaul - Migration from MongoDB to SQLite | [10 empty] | Daniel | Karen | Will | Will | bar: FY2017 May
Backend Overhaul - Migration from Bootstrap to Foundations | [10 empty] | Daniel | Karen | Will | Will | bar: FY2017 May
Virtual Tour Page - Use of Mapillary data with Household Overview data | [10 empty] | Daniel | Karen | Will | Will | bar: FY2017 Jun
Addition of 960 Latrine Page - Planning and consultation with WatSan Sector | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will | bar: FY2017 Apr
Additiona of 960 Latrine Page - Development of 960 Latrine Page | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will, Matt, Margaret, Sector Heads | bar: FY2017 Jun
Addition of CHAST Page - Planning and consultation with WatSan Sector | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will | bar: FY2017 Apr
Addition of CHAST Page - Development of CHAST Page | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will, Matt, Margaret, Sector Heads | bar: FY2017 Apr to FY2017 May
Addition of CMLP Page - Planning and consultation with WatSan Sector | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will | bar: FY2017 Apr
Additiona of CMLP Page - Development of CMLP Page | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will, Matt, Margaret, Sector Heads | bar: FY2017 Jun to FY2018 Jul
Addition of Health Page - Planning and consultation with Health Sector | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will | bar: FY2017 Apr
Addition of Health Page - Development of Health Page | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will, Matt, Margaret, Sector Heads | bar: FY2017 May
Addition of DRR Page - Planning and consultation with DRR Sector | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will | bar: FY2017 Apr
Addition of DRR Page - Development of DRR Page | [10 empty] | Karen | Karen | Will, Daniel, Nanette | Will, Matt, Margaret, Sector Heads | bar: FY2017 May to FY2017 Jun
Webviz Socialization
Infographic | [10 empty] | Ylla | Will | Will | Will, Matt, Sectors Heads | bar: FY2017 Mar
Introductory Video | [10 empty] | Ylla | Will | Will | Will, Matt, Sectors Heads | bar: FY2017 Mar
How-To Video | [10 empty] | Ylla | Will | Will | Will, Matt, Sectors Heads | bar: FY2017 Mar to FY2017 Apr
Webviz Transition
Review and consolidate documentation (Planning, Maintenance, Wireframes, Mock ups, Code, Backups) | [10 empty] | Karen | Karen | Will, Ernest | Will, Matt, Margaret, Pau | bar: FY2018 Sep
Develop maintenance guide | [10 empty] | Karen | Karen | Will, Ernest | Will, Matt, Margaret, Pau | bar: FY2018 Sep
Handover documentation and mainenance guide | [10 empty] | Karen | Karen | Will, Ernest | Will, Matt, Margaret, Pau | bar: FY2018 Sep
Support handover server (Postgresql, mac mini) | [10 empty] | Karen | Karen | Will, Ernest | Will, Matt, Margaret, Pau | bar: FY2018 Oct
Records Management
Draft Records Management Work Plan (Records List, Folder Structure, Access Permission, Migration) | [10 empty] | Karen | Karen | Will, Pau, IM Task Force | Will, Pau, IM Task Force | bar: FY2017 Mar
Support interim migration of document to TTL Shared Drive | [10 empty] | Karen | Karen | Will, Matt, Pau, IM Task Force, Sectors | Will, Matt, Pau, IM Task Force, Sectors | bar: FY2017 Apr
Support interim archiving of phyiscal documents | [10 empty] | Pau | Pau | Pau | Pau | bar: FY2018 Jul
Update Records List, Folder Structure, and Access Permissions | [10 empty] | Karen | Karen | Will, Matt, Pau, IM Task Force, Sectors | Will, Matt, Pau, IM Task Force, Sectors | bar: FY2017 Jun
Update IM Standard Operating Procedure | [10 empty] | Karen | Karen | Will, Matt, Pau, IM Task Force, Sectors | Will, Matt, Pau, IM Task Force, Sectors | bar: FY2017 Mar
Support final migration of documents to TTL Shared Drive | [10 empty] | Karen | Karen | Will, Matt, Pau, IM Task Force, Sectors | Will, Matt, Pau, IM Task Force, Sectors | bar: FY2018 Nov
Support final archiving of phyiscal documents | [10 empty] | Pau | Pau | Pau | Pau | bar: FY2018 Nov
List Management
960 Latrine list management | [10 empty] | Grace | Grace | Will, Nanette, | Will, Nanette, Aaron | bar: FY2017 Mar to FY2018 Sep
SRA Top-Up list management | [10 empty] | Grace | Grace | Will, Aaron | Will, Nanette, Aaron | bar: FY2017 May to FY2018 Oct
Development of comprehensive accountability system (Grace, Cherie)
Accountability Framework
Review and Finalize Accountability Framework | [10 empty] | Will | Grace | Will, Matt, Margaret | Will, Matt, Sector Heads | bar: FY2017 Mar to FY2017 Apr
Feedback Mechanism
Collection of community feedback | [10 empty] | Dina, Edna | Mhe | Grace | Will
Data entry of community feedback | [10 empty] | Angelica, Melody | Cherie | Grace | Will
Translation of community feedback from Waray-waray to English | [10 empty] | Cherie, Melody | Grace | Will | Will
Adding of responses to frequently asked questions | [10 empty] | Cherie, Mhe | Grace | Will | Will
Sending of community feedback to sectors | [10 empty] | Cherie | Grace | Will | Will
Gathering of responses from sectors | [10 empty] | Cherie, Mhe | Grace | Will, Sector Heads | Will
Checking and consolidation of responses obtained | [10 empty] | Grace | Grace | Will | Will
Sending of sector responses to HoO for approval | [10 empty] | Cherie | Grace | Will, Sector Heads | Will
HoO approval of the sector responses | [10 empty] | Matt | Sir Matt | Will, Margaert | Will
Translation of HoO approved responses from English to Waray | [10 empty] | Cherie, Melody | Grace | Will | Will
Printing of approved Waray-waray responses | [10 empty] | Grace | Grace | Will | Will
Delivery of approved Waray-waray responses to the community | [10 empty] | Dina, Edna | Cherie, Mhe | Grace | Will
Logging of response reciepts | [10 empty] | Angelica, Cherie, Grace | Grace | Will | Will
Community orientation on the closure of the feedback mechanism | [10 empty] | Grace | Grace | Will | Will | bar: FY2018 Oct to FY2018 Nov
Hand-over of consolidated feedback and responses to chapter | [10 empty] | Will | Will | Will | Will | bar: FY2018 Nov
Hand-over of feedback boxes and boards to community | [10 empty] | Grace | Grace | Will | Will | bar: FY2018 Nov
Accountability Reporting
Consolidate and summarize the field observation log | [10 empty] | Grace | Grace | Will | Will
Consolidate and summarize selected feedback | [10 empty] | Grace | Grace | Will | Will
Draft Monhtly Accountability Report | [10 empty] | Grace | Grace | Will | Bryan, Margaert, Matt | at least one per month
Draft Final Report on Accountability | [10 empty] | Will | Will | Will, Sectors, Matt | Bryan, Margaert, Matt | bar: FY2018 Nov
Beneficiary Communication
Procurment of missing information boards and feedback boxes | [10 empty] | Program Admin | Grace | Will, COs, Steve, Aaron | Will | bar: FY2017 Mar to FY2017 Apr
Support maintenance of information boards | [10 empty] | Dina, Ailene, Edna | Grace | Will, COs, Steve, Aaron | Will
Capacity building of PRC staff and volunteers on key M&E technical abilities (Will)
Brownbag Implementation
Scheduling of Brownbag Sessions | [10 empty] | Jake | Will | Matt, Sector Heads | Matt, Sector Heads, Haiyan Sector Heads
Brownbag on Photo Collection | [10 empty] | Ylla | Will | Will | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 Apr
Brownbag on FGD | [10 empty] | Will | Will | Will | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 Jun
Collection and documentation of lessons learned (Will)
Monthly Reflection Meeting
Monthly Delegation Report Sectoral Meetings | [10 empty] | Karen | Karen | Will, Sector Heads | Matt
QPR Reflection Meeting
Meting Preparation | [10 empty] | Jake | Will | Matt, Sector Heads | Matt, Margaret | bar: FY2017 Mar; FY2017 Jun; FY2018 Sep
QPR Reflection Meeting | [10 empty] | Will | Will | Matt, Sector Heads | Matt, Margaret | bar: FY2017 Apr; FY2018 Jul; FY2018 Oct
Leave Behind Learning Package
CCG AAR | [10 empty] | Will, Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 Apr
STED AAR | [10 empty] | Will, Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 Apr
PHAST AAR | [10 empty] | Will, Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 May
SRA AAR | [10 empty] | Will, Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 May
Core AAR | [10 empty] | Will, Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 May
IDEALS AAR | [10 empty] | Will, Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2017 May
CBHFA AAR | [10 empty] | Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Jul
CMLP AAR | [10 empty] | Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Jul
Agri-Extension AAR | [10 empty] | Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Jul
CHAST AAR | [10 empty] | Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Jul
Level 1 Water System | [10 empty] | Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Aug
Level 2 Water System | [10 empty] | Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Aug
CMDRR AAR | [10 empty] | Grace, Mhe | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Oct
Finance AAR | [10 empty] | Will | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Nov
Logistics AAR | [10 empty] | Will | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Nov
Procurement AAR | [10 empty] | Will | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Nov
HR AAR | [10 empty] | Will | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Dec
IT AAR | [10 empty] | Will | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Dec
Admin AAR | [10 empty] | Will | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Dec
M&E AAR | [10 empty] | Margaret | Will | Sectors Heads | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Dec
Draft of Learning Package | [10 empty] | Will | Will | Sectors Heads, Matt, Margaret | Matt, Sector Heads, Haiyan Sector Heads | bar: FY2018 Sep to FY2018 Dec
Promotion of strategic communications (Ylla)
Success Story Collection | [14 empty] | at least 2 stories finalized per month
Interview and draft story | [10 empty] | Cherie, Mhe | Ylla | Will, Sectors | Will | interviews on 1st and 3rd week of month | bar: FY2017 Mar to FY2018 Sep
Edit story | [10 empty] | Ylla | Ylla | Will | Will | bar: FY2017 Mar to FY2018 Sep
Finalize story | [10 empty] | Cherie, Mhe,Ylla | Ylla | Will | Will | bar: FY2017 Mar to FY2018 Sep
Design of "Photo Story" | [10 empty] | Ylla | Ylla | Will | Will, Sector | bar: FY2017 Mar to FY2018 Sep
Disseminate story | [10 empty] | Ylla | Ylla | Will | Will, Sector | stories sent to sectors, haiyan task force sector | bar: FY2017 Mar to FY2018 Sep
Storage of story | [10 empty] | Ylla | Ylla | Will | Will, Karen, Sector, Matt | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Mar to FY2018 Sep
MSC Video Collection | [14 empty] | at least 3 videos per barangay
Collection of MSC | [10 empty] | Cherie, Mhe | Ylla | Will | Will | interviews on 1st and 3rd week of month | bar: FY2017 Mar to FY2018 Oct
Video editing (translation and subs) | [10 empty] | Cherie, Mhe | Ylla | Will | Will | bar: FY2017 Mar to FY2018 Oct
Finalize video | [10 empty] | Cherie,Mhe, Ylla | Ylla | Will | Will | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Mar to FY2018 Oct
Photo Collection | [14 empty] | at least 1 per major intervention
Timelapse - Wooden Core House | [10 empty] | Dina | Ylla | Will, Shelter | Matt, Will, Shelter | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Mar to FY2017 Apr
IDEALS | [10 empty] | Dina, Mhe | Ylla | Will, Shelter | Matt, Will, Shelter | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Mar
CMLP (each association) | [10 empty] | Ailene, Mhe | Ylla | Will, Livelihoods | Matt, Will, Livelihoods | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May to FY2017 Jun
Small Group Enterprises | [10 empty] | Ailene, Mhe | Ylla | Will, Livelihoods | Matt, Will, Livelihoods | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May to FY2017 Jun
CB STED | [10 empty] | Ailene, Mhe | Ylla | Will, Livelihoods | Matt, Will, Livelihoods | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May to FY2017 Jun
Contingency Planning | [10 empty] | Ailene, Mhe | Ylla | Will, DRR | Matt, Will, DRR | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May
DRR in Schools | [10 empty] | Ailene, Mhe | Ylla | Will, DRR | Matt, Will, DRR | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Jun to FY2018 Jul
Drills and Simulations | [10 empty] | Ailene, Mhe | Ylla | Will, DRR | Matt, Will, DRR | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Jun to FY2018 Sep
SRA Latrine | [10 empty] | Edna, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May to FY2017 Jun
Level 1 Construction | [10 empty] | Edna, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May to FY2017 Jun
Level 2 Construction | [10 empty] | Edna, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May to FY2017 Jun
Multi-Purpose Halls (each hall) | [10 empty] | Dina, Mhe | Ylla | Will, Infrastructure | Matt, Will, Infrastructure | storage in shared drive, webviz (gallery), tv content | bar: FY2018 Sep to FY2018 Oct
Stepped Pathway | [10 empty] | Dina, Mhe | Ylla | Will, Infrastructure | Matt, Will, Infrastructure | storage in shared drive, webviz (gallery), tv content | bar: FY2018 Oct to FY2018 Dec
CHAST | [10 empty] | Edna, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Mar to FY2017 May
BAWASA | [10 empty] | Edna, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Mar to FY2017 Apr
School Water System (each school) | [10 empty] | Edna, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May to FY2018 Aug
Villa Imelda | [10 empty] | Dina | Ylla | Will, Shelter | Matt, Will, Shelter | storage in shared drive, webviz (gallery), tv content | bar: FY2018 Sep to FY2018 Dec
Video Collection
Solar lights installation and elumination | [10 empty] | Ylla, Mhe | Ylla | Will, Infrastucture | Matt, Will, Infrastucture | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Mar to FY2017 Apr
Stepped pathway construction | [10 empty] | Ylla, Mhe | Ylla | Will, Infrastucture | Matt, Will, Infrastucture | storage in shared drive, webviz (gallery), tv content | bar: FY2018 Oct to FY2018 Nov
Multi-purpose hall construction | [10 empty] | Ylla, Mhe | Ylla | Will, Infrastucture | Matt, Will, Infrastucture | storage in shared drive, webviz (gallery), tv content | bar: FY2018 Oct to FY2018 Nov
Villa Imelda construction | [10 empty] | Ylla, Mhe | Ylla | Will, Infrastucture, Shelter | Matt, Will, Infrastucture, Shelter | storage in shared drive, webviz (gallery), tv content | bar: FY2018 Aug to FY2018 Nov
Level-1 water system construction | [10 empty] | Ylla, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 Apr
Level-2 water system construction | [10 empty] | Ylla, Mhe | Ylla | Will, WASH | Matt, Will, WASH | storage in shared drive, webviz (gallery), tv content | bar: FY2017 May
Barangay summary video pilot | [10 empty] | Ylla | Ylla | Will, Matt, Sectors, CO | Will, Matt, Sectors, CO | bar: FY2017 Apr
Barangay summary video footage collection | [10 empty] | Ylla | Ylla | Will, Sectors, CO | Will, Matt, Sectors, CO | bar: FY2017 May to FY2018 Sep
Barangay summary video stitching | [10 empty] | Ylla | Ylla | Will, Sectors, CO | Will, Matt, Sectors, CO | bar: FY2018 Aug to FY2018 Nov
Barangay summary video finalization | [10 empty] | Ylla | Ylla | Will, Matt, Sectors, CO | Will, Matt, Sectors, CO | storage in shared drive, webviz (gallery), tv content | bar: FY2018 Nov to FY2018 Dec
Mapping Support
Drone flight concept note and memo | [10 empty] | Will | Will | Will, Margaert, Matt, Friday, Daniel | Matt, Margaret | bar: FY2017 Mar
Drone flight PCAA wavier | [10 empty] | Will | Will | Will, Daniel, Margaret | Will, Daniel, Matt, Margaret | bar: FY2017 Mar
Drone flight admin support | [10 empty] | Program Admin | Will | Will | Will | bar: FY2017 Apr
Drone flight | [10 empty] | Daniel | Will | Will, Daniel, Matt, Friday, Margaret | Will, Daniel, Matt, Friday, Margaret | bar: FY2017 May
Procurement for printing of imagery | [10 empty] | Program Admin | Will | Will | Matt, Margaret | bar: FY2017 May to FY2017 Jun
Printing of imagery | [10 empty] | Program Admin | Will | Will, COs | Matt, Margaret | bar: FY2018 Jul to FY2018 Aug
Mapillary data collection | [10 empty] | Dina, Ailene, Edna | Karen | Will, COs, Daniel | Daniel | bar: FY2017 Mar to FY2018 Oct
Mapillary upload | [10 empty] | Karen | Karen | Will, Daniel | Matt, Margaret | bar: FY2017 Mar to FY2018 Oct
Graphic Design
Barangay Profiles | [10 empty] | Ylla | Ylla | Will, Sectors, CO | Will, Sectors, CO | bar: FY2017 Mar; FY2017 Jun; FY2018 Sep; FY2018 Dec
Barangay Org Charts | [10 empty] | Ylla | Ylla | Will, Sectors, CO | Will, Sectors, CO | bar: FY2017 Mar; FY2017 Jun; FY2018 Sep; FY2018 Dec
Project Summaries | [10 empty] | Ylla | Ylla | Will, Matt, Sectors, CO | Will, Matt, Sectors, CO | bar: FY2017 Mar; FY2017 Jun; FY2018 Sep; FY2018 Dec
TTL Overview Presentation | [10 empty] | Ylla | Ylla | Will, Matt | Will, Matt | bar: FY2017 Mar; FY2017 Jun; FY2018 Sep; FY2018 Dec
Delegation Overview Presentation | [10 empty] | Ylla | Ylla | Will, Matt, Margaret | Will, Matt, Margaret | bar: FY2017 Mar; FY2017 Jun; FY2018 Sep; FY2018 Dec
Special Projects - CMLP Overview | [10 empty] | Ylla | Ylla | Will, Livelihoods | Will, Matt, Margaret | bar: FY2017 May
TV Content Management
HR updates | [10 empty] | Murphy | Mhe | Ylla | Will | bar: FY2017 Mar to FY2018 Oct
Staff on leave | [10 empty] | Murphy | Mhe | Ylla | Will | bar: FY2017 Mar to FY2018 Oct
Monthly birthdays | [10 empty] | Ruth | Mhe | Ylla | Will | bar: FY2017 Mar to FY2018 Oct
MSC Videos | [10 empty] | Cherie, Mhe | Mhe | Ylla | Will | bar: FY2017 Mar to FY2018 Oct
Photo Stories | [10 empty] | Ylla | Mhe | Ylla | Will | bar: FY2017 Mar to FY2018 Oct
Project Summaries | [10 empty] | Ylla | Mhe | Ylla | Will | bar: FY2017 Mar to FY2018 Oct
Infographics (Reporting process, training process map, etc) | [10 empty] | Ylla | Mhe | Ylla | Will | bar: FY2017 Mar to FY2018 Oct

## Unit Workplan Costs Budget CY15 (hidden)
Budget Line | Sector | Activity Code | Description | Spent to Date | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | FY 15 Budget Total (USD) | Original Proposal Budget (USD)
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
TTL 131 | Monitoring & Evaluation | 404 | GIS Advanced mobile data collection (survey creation, etc.) (4 days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400
TTL 132 | Monitoring & Evaluation | 400 | GIS Advanced excel (2 days) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200
TTL 133 | Monitoring & Evaluation | 400 | GIS Analyzing data (basic) (1-2 days) 5 Trainings for TTL staff & volunteers | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.5455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 454.5455 | 500
TTL 134 | Monitoring & Evaluation | 404 | GIS Mobile data collection (1 day, 15-20 volunteers) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
TTL 135 | Monitoring & Evaluation | 404 | GIS Mobile data collection (advanced) (3 days, 3 staff) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
TTL 136 | Monitoring & Evaluation | 401 | GIS Participatory GIS workshop (3 days, only GIS staff) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
TTL 137 | Monitoring & Evaluation | 400 | GIS GIS field methods (GPS, etc.) training (1 day, 6-8 volunteers) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100
TTL 138 | Monitoring & Evaluation | 400 | GIS OpenStreetMap training (3 days, only GIS staff) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
TTL 176 | Monitoring & Evaluation | 401 | AtB orientation workshop (TT.D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409.0909 | 0 | 0 | 0 | 0 | 0 | 409.0909 | 1680
TTL 177 | Monitoring & Evaluation | 405 | AtB implementation in each Barangay | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209.0909 | 0 | 0 | 0 | 209.0909 | 36000
TTL 178 | Monitoring & Evaluation | 405 | Participatory M&E in BareComs (TT.D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522.7273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 522.7273 | 5040
TTL 179 | Monitoring & Evaluation | 405 | Programme Monitoring (5 municipalities 2 events/year) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000
TTL 180 | Monitoring & Evaluation | 405 | Internal Programme Reviews | 0 | 0 | 0 | 0 | 4318.1818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4318.1818 | 12980
TTL 181 | Monitoring & Evaluation | 405 | M&E Capacity Building | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
TTL 182 | Monitoring & Evaluation | 405 | Participatory Evaluation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14400
TTL 323 | Monitoring & Evaluation | 405 | GIS workstation x4 | 0 | 0 | 0 | 0 | 909.0909 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 909.0909 | 6000
TTL 324 | Monitoring & Evaluation | 405 | GIS workstation Monitors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500
TTL 325 | Monitoring & Evaluation | 405 | GPS Devices | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000
TTL 330 | Monitoring & Evaluation | 405 | License Adobe Creative Suite | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 1000
TTL 331 | Monitoring & Evaluation | 405 | License Tableau (non profit rate) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500
TTL 332 | Monitoring & Evaluation | 405 | ARC GIS license | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300
TTL 340 | Monitoring & Evaluation | 405 | Plotter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
TTL 342 | Monitoring & Evaluation | 405 | GPS/ODK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000
TTL 370 | Monitoring & Evaluation | 405 | GIS Software Customization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000
[21 empty] | 7422.7273 | 130600
GM | N/A | N/A | Baseline Study | 0 | [16 empty] | N/A | N/A
GM | N/A | N/A | Endline Study | 0 | [16 empty] | N/A | N/A
GM | N/A | N/A | External Evaluation | 0 | [16 empty] | N/A | N/A
Budget Line | Sector | Activity Code | Description | Spent to Date | September Week 1: September; October Week 1: October; November Week 1: November; December Week 1: December | FY 15 Budget Total (PHP) | Original Proposal Budget (PHP)
[5 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
TTL 131 | Monitoring & Evaluation | 404 | GIS Advanced mobile data collection (survey creation, etc.) (4 days) | 0 | [16 empty] | 0 | 17600
TTL 132 | Monitoring & Evaluation | 400 | GIS Advanced excel (2 days) | 0 | [16 empty] | 0 | 8800
TTL 133 | Monitoring & Evaluation | 400 | GIS Analyzing data (basic) (1-2 days) 5 Trainings for TTL staff & volunteers | 0 | November Week 1: 20000 | 20000 | 22000
TTL 134 | Monitoring & Evaluation | 404 | GIS Mobile data collection (1 day, 15-20 volunteers) | 0 | [16 empty] | 0 | 4400
TTL 135 | Monitoring & Evaluation | 404 | GIS Mobile data collection (advanced) (3 days, 3 staff) | 0 | [16 empty] | 0 | 13200
TTL 136 | Monitoring & Evaluation | 401 | GIS Participatory GIS workshop (3 days, only GIS staff) | 0 | [16 empty] | 0 | 13200
TTL 137 | Monitoring & Evaluation | 400 | GIS GIS field methods (GPS, etc.) training (1 day, 6-8 volunteers) | 0 | [16 empty] | 0 | 4400
TTL 138 | Monitoring & Evaluation | 400 | GIS OpenStreetMap training (3 days, only GIS staff) | 0 | [16 empty] | 0 | 13200
TTL 176 | Monitoring & Evaluation | 401 | AtB orientation workshop (TT.D) | 0 | November Week 3: 18000 | 18000 | 73920
TTL 177 | Monitoring & Evaluation | 405 | AtB implementation in each Barangay | 0 | December Week 1: 9200 | 9200 | 1584000
TTL 178 | Monitoring & Evaluation | 405 | Participatory M&E in BareComs (TT.D) | 0 | October Week 3: 23000 | 23000 | 221760
TTL 179 | Monitoring & Evaluation | 405 | Programme Monitoring (5 municipalities 2 events/year) | 0 | [16 empty] | 0 | 660000
TTL 180 | Monitoring & Evaluation | 405 | Internal Programme Reviews | 0 | September Week 4: 190000 | 190000 | 571120
TTL 181 | Monitoring & Evaluation | 405 | M&E Capacity Building | 0 | [16 empty] | 0 | 396000
TTL 182 | Monitoring & Evaluation | 405 | Participatory Evaluation | 0 | [16 empty] | 0 | 633600
TTL 323 | Monitoring & Evaluation | 405 | GIS workstation x4 | 0 | September Week 4: 40000 | 40000 | 264000
TTL 324 | Monitoring & Evaluation | 405 | GIS workstation Monitors | 0 | [16 empty] | 0 | 110000
TTL 325 | Monitoring & Evaluation | 405 | GPS Devices | 0 | [16 empty] | 0 | 132000
TTL 330 | Monitoring & Evaluation | 405 | License Adobe Creative Suite | 0 | September Week 4: 26400 | 26400 | 44000
TTL 331 | Monitoring & Evaluation | 405 | License Tableau (non profit rate) | 0 | [16 empty] | 0 | 66000
TTL 332 | Monitoring & Evaluation | 405 | ARC GIS license | 0 | [16 empty] | 0 | 13200
TTL 340 | Monitoring & Evaluation | 405 | Plotter | 0 | [16 empty] | 0 | 44000
TTL 342 | Monitoring & Evaluation | 405 | GPS/ODK | 0 | [16 empty] | 0 | 396000
TTL 370 | Monitoring & Evaluation | 405 | GIS Software Customization | 0 | [16 empty] | 0 | 440000
[21 empty] | 326600 | 5746400
GM | N/A | N/A | Baseline Study | 0 | [16 empty] | N/A | N/A
GM | N/A | N/A | Endline Study | 0 | [16 empty] | N/A | N/A
GM | N/A | N/A | External Evaluation | 0 | [16 empty] | N/A | N/A
0

## Unit Workplan Costs Budget LOP (hidden)
Budget Line | Sector | Activity Code | Description | Spent to Date | Feb FY15 | Mar FY15 | Apr FY15 | May FY15 | Jun FY15 |  | Jul FY16 | Aug FY16 | Sep FY16 | Oct FY16 | Nov FY16 | Dec FY16 | Jan FY16 | Feb FY16 | Mar FY16 | Apr FY16 | May FY16 | Jun FY16 |  | Jul FY17 | Aug FY17 | Sep FY17 | Oct FY17 | Nov FY17 | Dec FY17 | Jan FY17 | Feb FY17 | Mar FY17 | Apr FY17 | May FY17 | Jun FY17 | Estimated Expenditure | Original Proposal Budget | Expected Budget Deviation
TTL 131 | Monitoring & Evaluation | 404 | GIS Advanced mobile data collection (survey creation, etc.) (4 days) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 400 | #REF!
TTL 132 | Monitoring & Evaluation | 400 | GIS Advanced excel (2 days) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 200 | #REF!
TTL 133 | Monitoring & Evaluation | 400 | GIS Analyzing data (basic) (1-2 days) 5 Trainings for TTL staff & volunteers |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 500 | #REF!
TTL 134 | Monitoring & Evaluation | 404 | GIS Mobile data collection (1 day, 15-20 volunteers) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 100 | #REF!
TTL 135 | Monitoring & Evaluation | 404 | GIS Mobile data collection (advanced) (3 days, 3 staff) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 300 | #REF!
TTL 136 | Monitoring & Evaluation | 401 | GIS Participatory GIS workshop (3 days, only GIS staff) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 300 | #REF!
TTL 137 | Monitoring & Evaluation | 400 | GIS GIS field methods (GPS, etc.) training (1 day, 6-8 volunteers) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 100 | #REF!
TTL 138 | Monitoring & Evaluation | 400 | GIS OpenStreetMap training (3 days, only GIS staff) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 300 | #REF!
TTL 176 | Monitoring & Evaluation | 401 | AtB orientation workshop (TT.D) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 1680 | #REF!
TTL 177 | Monitoring & Evaluation | 405 | AtB implementation in each Barangay |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | 3000 | 6000 | 7500 | 7500 | 7500 | [20 empty] | #REF! | 36000 | #REF!
TTL 178 | Monitoring & Evaluation | 405 | Participatory M&E in BareComs (TT.D) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | 522.7273 | [21 empty] | #REF! | 5040 | #REF!
TTL 179 | Monitoring & Evaluation | 405 | Programme Monitoring (5 municipalities 2 events/year) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  |  |  |  | 3750 | [5 empty] | 3750 | [13 empty] | #REF! | 15000 | #REF!
TTL 180 | Monitoring & Evaluation | 405 | Internal Programme Reviews |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [24 empty] | #REF! | 12980 | #REF!
TTL 181 | Monitoring & Evaluation | 405 | M&E Capacity Building |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 9000 | #REF!
TTL 182 | Monitoring & Evaluation | 405 | Participatory Evaluation |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [11 empty] | 2000 | 2000 | 2000 | 2000 | [8 empty] | #REF! | 14400 | #REF!
TTL 323 | Monitoring & Evaluation | 405 | GIS workstation x4 |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | 909.0909 | [22 empty] | #REF! | 6000 | #REF!
TTL 324 | Monitoring & Evaluation | 405 | GIS workstation Monitors |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 2500 | #REF!
TTL 325 | Monitoring & Evaluation | 405 | GPS Devices |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 3000 | #REF!
TTL 330 | Monitoring & Evaluation | 405 | License Adobe Creative Suite |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | 600 | [22 empty] | #REF! | 1000 | #REF!
TTL 331 | Monitoring & Evaluation | 405 | License Tableau (non profit rate) |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 1500 | #REF!
TTL 332 | Monitoring & Evaluation | 405 | ARC GIS license |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 300 | #REF!
TTL 340 | Monitoring & Evaluation | 405 | Plotter |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 1000 | #REF!
TTL 342 | Monitoring & Evaluation | 405 | GPS/ODK |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 9000 | #REF!
TTL 370 | Monitoring & Evaluation | 405 | GIS Software Customization |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | [23 empty] | #REF! | 10000 | #REF!
Subtotal - Itemized |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 9009.0909 | 8022.7273 | 7500 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | 130600 | #REF!
GM | N/A | N/A | Baseline Study |  | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | [24 empty] | #REF! | N/A | N/A
GM | N/A | N/A | Endline Study | [7 empty] | #REF! | [18 empty] | 12000 | 12000 | 6000 |  |  |  | #REF! | N/A | N/A
GM | N/A | N/A | External Evaluation | [7 empty] | #REF! | #REF! | [7 empty] | 6000 | 6000 | [8 empty] | 6000 | 6000 |  |  |  |  | #REF! | N/A | N/A
Subtotal - Consultancy |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6000 | 6000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18000 | 18000 | 6000 | 0 | 0 | 0 | #REF! | N/A | N/A
Total |  |  |  | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | #REF! | #REF! | 9009.0909 | 8022.7273 | 7500 | 3750 | 0 | 0 | 0 | 6000 | 6000 | 3750 | 0 | 2000 | 2000 | 2000 | 2000 | 0 | 0 | 18000 | 18000 | 6000 | 0 | 0 | 0 | #REF! | N/A | N/A

## Management Tracker (hidden)
Task | Date Completed | Responsible Person
Key Initiatives/Priorities
Finalize Project LogFrame |  | Will
Update Project LogFrame |  | Will
Finalize Project M&E Plan |  | Will
Finalize AtoB Plan |  | Will, Tonette
Baseline TOR Completed |  | Grace, Cherie, Will
Baseline Data Collection Started |  | Grace, Cherie, Will
Baseline Data Shared with Community |  | Grace, Cherie, Will
Baseline Report Completed |  | Grace, Cherie, Will
Operationalize Database |  | Will, Dan
Finalize Monitoring Tools |  | Grace, Cherie
Update Monitoring Tools - 1 |  | Grace, Cherie
Update Monitoring Tools - 2 |  | Grace, Cherie
Update Monitoring Tools - 3 |  | Grace, Cherie
Review Targets |  | Grace, Cherie, Will
QPR Composition - 1 |  | Will, Jo, Margaret
QPR Composition - 2 |  | Will, Jo, Margaret
QPR Composition - 3 |  | Will, Jo, Margaret
QPR Composition - 4 |  | Will, Jo, Margaret
Monthly Report Composition - 1 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 2 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 3 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 4 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 5 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 6 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 7 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 8 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 9 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 10 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 11 |  | Will, Nica, Jo, Margaret
Monthly Report Composition - 12 |  | Will, Nica, Jo, Margaret
Unit Plan Completed |  | Will
Unit Plan Reviewed - 1 |  | Will
Unit Plan Reviewed - 2 |  | Will
Unit Plan Reviewed - 3 |  | Will
Unit Plan Reviewed - 4 |  | Will
Unit Plan Reviewed - 5 |  | Will
Unit Plan Reviewed - 6 |  | Will
Unit Plan Reviewed - 7 |  | Will
Unit Plan Reviewed - 8 |  | Will
Unit Plan Reviewed - 9 |  | Will
Unit Plan Reviewed - 10 |  | Will
Unit Plan Reviewed - 11 |  | Will
Unit Plan Reviewed - 12 |  | Will
Staffing
Advertisment GIS Staff |  | Will, Nica
Hiring and Training of GIS Staff |  | Will, Nica, Dan
Procurment of GIS equipment |  | Will, Nica
Capacity Building
Quality Assurance
Risk Management
Coordination & Stakeholder Relations
Other