## Casual Pathway Livelihoods (hidden)
Activities | Outputs | Indicators - Livelihoods | Outcome | Outcome Indicators - Livelihoods | Objective | Impact
Objective 1.
| 1.1.1 PRC staff and volunteers trained and mentored in project management, core community implementation sectors and cross cutting approaches | # of PRC staff and volunteers trained project management # of core sector trainings provided # of PRC staff who participate in corse sector trainings | 1.1 PRC HQ and Leyte Branch have increased capacity to implement integrated recovery program | % of PRC staff and volunteers trained in RCRC sector and/or cross cutting approaches who demonstrate increased knowledge | 1. Increase PRC capacity in community based recovery and preparednes to enhance community resilience over a 3 year period | Safer, More Resilient Communities
| 1.2.1 143 Volunteers available in each Barangary across the program areas | # targeted barangays with 143 teams # of community members trained to be part of 143 teams in targeted barangays | 1.2 PRC Leyte branch and targeted communities have active network of RC volunteers | % of targeted communities that have a PRC 143 team
| 1.2.2. PRC Leyte branch capacity to respond to disastered enhanced | Organizal and DM Capacity Assessment Completed Branch Capacity Development Plans for DM implemented Improved volunteer mobilization systems (including Leyte Branch database)
Objective 2
| 2.1.1. Targeted communities have improved organiztion and collective capacity to act effectively in the event of disasters and shocks | # of beracom formed in the target communities | 2.1 Targeted communities are organized and have improved disaster safety and resilience | % of active teams/committees for WASH, Health and DRR/DP functioning within targeted communities | 2. To increase community capacity to adopt resilient practices
# of community manged projects supported through cash grant trainings
| 2.2.1 Community members are trained in topic of project intervention | # of community members trained in livelihood activity | 2.2 Community members have increased knowledge and skills to support their recovery and resilience | % of community members/volunteers who participated in shelter (PASSA), livelihoods, WASH (PHAST), health, DRR & DP skills development has increased knowledge on skills covered
| 2.4.1 Targeted communities have access to financial services through Gcash Mobile Money | # of HH that receive Gcash Mobile Money # of new stores in targeted communities registered as Gcash Agents | 2.4 People asssisted with livelihooods support had increased and sustainable income | % of HH/SMEs have increased and sustained income as a result of support received by program activities
| 2.4.2. Marketable community and household lilvlihood activities are supported with improved marketing techniques and sustainable market linkages | # of people provided with marketable Livelihood Activitiy trainings
SME Development Community SME of Cooperative |  | # of small and medium enterprises given financial support
# of inidividual or businesses supported to deevlop marketing plans
# of community members certified as carpenter or masons or chainsaw operators, etc
Conditional Cash Distribution | 2.4.3 Asset replaced or provided for community-driven and/or householdl | # of HH provided with Conditional Cash grant for assets replacement

## Draft Logframe - Original (hidden)
TINDOG TABANG LEYTENA LOGFRAME
Results Chain/Design Level | Indicators | Targets | Data Source/ Verification | Assumptions | FWRS Ref | Accountability
GOAL: To contribute to building safe and resilient communities by identifying and addressing various factors that will help people sustainably rebuild their lives, livelihoods and assets while ensuring that future climate, environmental and disaster related risks are addressed and/or minimized
Objective 1: To increase PRC capacity in community based recovery and preparedness to enhance community resilience over a 3 year period.
Outcome 1.1. PRC HQ and Leyte Branch has increase capacity to implement integrated recovery program | PRC Leyte staff have improved skills in project management/PMER (qualitative) |  | Baseline, End of project evaluation Report
| % of PASSA trained staff/volunteers led PASSA process in communities |  | PASSA implementation Reports
| % of PRC staff and volunteers trained in RCRC Sector Modules and cross cutting approaches who demonstate increased knowledge |  | Pre-Post Test, Evaluation
Output 1.1.1: PRC staff and volunteers trained and mentored in project management, core community implementation sectors and cross cutting approaches | # of PRC staff and volunteers trained in project management |  | Training Reports
| # of core sector trainings provided (Shelter, Livelihoods, WatSan, Health, DRR & DP) |  | Training Reports |  | F4
| # of PRC staff and volunteers participated in core sectors trainings |  | Training Reports
| # of people trained in shelter technical training – (PRC HQ, Branch etc.) |  | Training Reports
| # of staff/volunteers participated in PASSA TOT |  | Training Reports
| # of staff/volunteers trained as PASSA facilitators |  | Training Reports
Outcome 1.2: PRC Leyte branch and targeted communities have active network of RC volunteers | % of targeted communities that have an PRC 143 teams (to be defined) |  | Monitoring Reports
PRC Leyte brach have improved capacity to respond to disasters (qualitative)
Output 1.2.1: 143 Volunteers available in each Barangay across the program area | # of targeted barangays with 143 teams |  | Training Reports |  | F1
| # of community members trained to be part of 143 team in targeted barangays |  | Training Reports
Output 1.2.2: PRC Leyte branch capacity to respond to disaster enhanced | Organizational and DM Capacity assessment of PRC Leyte Branch completed (qualitative) |  | Assessment Report
| Branch’s Capacity Development Plans for DM implemented in coordination PRCNHQ/IFRC/PNS (qualitative) |  | Monitoring Reports
| Improve volunteer mobilization system including database in PRC Leyte Branch (Qualitative) |  | Volunteer Database
| # of staff/volunteers trained in use of IFRC shelter kit |  | Training Reports
| # staff/volunteers trained in FA/PFA |  | Training Reports
Obj. 2: To increase Communities capacity to adopt resilient practices
Outcome 2.1: Targeted communities are organized and have improved disaster safety and resilience. | % of active teams/committees for WASH , Health and DRR/DP functioning within targeted communities |  | Baseline, End of project evaluation Report
| % of people who participated in a disaster simulation/drill in last year |  | Baseline-Endline Survey
| % of family with disaster preparedness plan |  | Baseline-Endline Survey
| % of HH aware about community based early warning system |  | Baseline-Endline Survey
Output 2.1.1: Targeted communities have improved organization and collective capacity to act effectively in the event of disasters and shocks | Number of community DRR plans developed based on assessment findings |  | Assessment Report | Communities willing to engage with mobilization efforts | F6
| # of beracom formed in the targeted communities |  | Monitoring Reports
| # of community managed projects supported through cash grant, trainings. |  | Monitoring Reports |  | B8
Output 2.1.2: Targeted individual and communities have increased awareness and knowledge of disaster preparedness practices | # of community simulation and drill organized |  | Monitoring Reports | Communities have willing to participate and can carry out Recovery and DRR activities.
| # of people participated in community simulation and drills |  | Monitoring Reports
| # of people reached with DRR/DP messages |  | Monitoring Reports
Outcome 2.2: Community members have increased knowledge and skills to support their recovery and resilience | % of community member who participated in PASSA is aware about shelter related risk. |  | Baseline-Endline Survey, Pre-Post test
| % of community members/volunteers who participated in shelter (PASSA), livelihoods, WASH (PHAST), health, DRR & DP skills development has increased knowledge on the subjects covered. |  | Baseline-Endline Survey, Pre-Post test
Output 2.2.1: Community members are trained in topic of project intervention | # of community action plan prepared as a result of adapted PASSA |  | Monitoring Reports |  | A10/D4
| # of community members participated in PASSA process |  | Monitoring Reports
| # of community members trained in livelihood activity |  | Training Reports
| # of community members trained in PHAST |  | Training Reports
| # of community members trained in DRR and DP |  | Training Reports
| # of community members trained in health services |  | Training Reports |  | D3
| # of BHW & BNS trained in technical topics and First Aid based on training needs assessments |  | Training Reports |  | D3
Outcome 2.3.: Community members follow safer and healthierpractices that reflect their increased knowledge and skills | % of HH those who received shelter repair or retrofit kit using safe shelter practices at their house. |  | Monitoring Visits
| % of people aware about safe disposal (separating, recycle, reuse, composting, etc.) of HH solid waste |  | Baseline-Endline Survey
| % of people aware about safe heath or hygiene practices (TBD after assessment, e.g. Hand washing,etc) |  | Baseline-Endline Survey
| % or HH with safer and healthier practices to reduce risk of hazards (fire, illness, etc.) |  | Baseline-Endline Survey
| % of houses with screens on windows to prevent mosquito entry (for other than core houses) |  | Baseline-Endline Survey
Output2.3.1: Community member participated in safe construction practices | # of HH members participated in the construction process. |  | Monitoring Reports
| # of HH member received orientation of safe shelter (construction, repair kits, retrofit etc.) |  | Training Reports
| # of HHs assisted to increased their security of tenure |  | Monitoring Reports
Output 2.3.2: Community participated in PHAST implementation | # of community action plan updated after PHAST implementation |  | Monitoring Reports
| # of community members participating in PHAST activities by Barangay, age and sex |  | Monitoring Reports
| # of people reached by health/hygiene promotion activities |  | Monitoring Reports |  | C7/D6
Outcome 2:4: People assisted with livelihood support had increased and sustainable income | % of HH/SME have increased and sustained income as a result of support received by program activities
Output 2.4.1 Targeted communities have access to financial services through GCash Mobile Money. | # of HH that receive GCash Mobile Money | 1) 50% of targeted HH | GCash Reconciliation Reports
| # of new stores in targeted communities registered as Gcash Agents | 1) 1 transaction per participating HH receiving CCG | Monitoring Reports
Output 2.4.2 Marketable community and household livelihood activities are supported with improved marketing techniques and sustainable market linkages | # of people provided with marketable Livelihood Activities training | 1) 25% of supported livelihood activities | Training Reports |  | B5
| # of small and medium enterprises given financial support | 1) 25% of supported livelihood activities | Monitoring Reports |  | B7
| # of individual or business supported to develop marketing plan. |  | Monitoring Reports
| # of community member certified as carpenter or masons or chainsaw operators, etc. |  | Training Reports |  | B5
Output 2.4.3: Assets replaced or provided for community-driven and/or household livelihood activities through Conditional Cash Grants. | # of HH provided with Conditional Cash grant for assets replacement |  | Monitoring Reports
Objective 3: Increase household and community access to safer and sustainable infrastructure and resources within a 3 year period
Outcome 3.1: Increased community capacity to manage its physical environment through infrastructure and resources. | % of community water and sanitation committee regularly (in last three months) collects fees in order to maintain facility from users |  | Baseline, End of project evaluation Report
| % of facilities repaired by community water and sanitation committee with their resources |  | Monitoring Reports
| % of HH who improved/repaired their shelter after handover with their own resources |  | Endline Survey
People report that their community is more safer and resilient (qualitative)
Output 3.1.1: Targeted HH has a safe shelter with sanitation facilities | # of HH provided with a core shelter with sanitation facilities |  | Monitoring Reports |  | A3/C5
| # of HH provided with a shelter repair assistance |  | Monitoring Reports |  | A4
| # of HH provided with a shelter retrofit assistance |  | Monitoring Reports |  | A4
| # of HH provided with a shelter solution in relocation site |  | Monitoring Reports |  | A5
| # of HH provided with alternate shelter solutions (rental, host family, etc.) |  | Monitoring Reports |  | A5
# of barangaya with completed HH profiles
Outcome 3.2 Increased access to health services, safe water and reduce exposure to hazards within the barangay | % of barangay members who report improved access to health services in the barangay |  | Baseline-Endline Survey
| % of water systems tested whose water quality meets the criteria as per national standard. |  | Monitoring Reports
Output 3.2.1: Improved public infrastructure in the targeted communities | # of health facilities/schools/public places repaired/reconstructed |  | Monitoring Reports |  | A6
| # of community (public) facilities provided with improved (repaired or constructed) water and sanitation facilities |  | Monitoring Reports |  | C6
| # of mitigation projects completed to reduce hazards in the targeted communities |  | Monitoring Reports
| # of health facilities re-equipped with basic equipment's (e.g. BP machine, weighing scale, etc.) |  | Monitoring Reports |  | A6
| # of schools and community centers rehabilitated or retrofitted as safer emergency evacuation spaces |  | Monitoring Reports
Cross cutting | Estimated total # of people reached by RCRC services |  |  |  | G1 | x
| # of HH/families reached with program |  |  |  |  | x
| # of HHs/Families provided with safe shelter solutions (core + repair + rental, etc.) |  |  |  |  | x
| # of community member received training on project interventions |  |  |  |  | x
| # of staff and volunteers received training |  |  |  |  | x
# of Barangaya reached
.
Note on D44: Ranjan Mohnot: (every quarter out of those who monitored, one household will be monitored multiple times, all household will be visited)
Note on B65: Ranjan Mohnot: (# of repair done by community WatSan committee/number of problem (non-functioning) reported)

## M&E Plan
M&E Indicator Plan
Associated Activities | Indicator | Indicator Definition | Data Collection Method | Data Collection Frequency | Person Responsible | Information Use
Roll out of harmonized participatory tools + implementation sessions | % of key PRC Leyte chapter teams or functional areas with improved skills in project management/PMER | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of key PRC Leyte teams/functional areas whose staff have improved skills in project management/PMER. Key PRC Leyte teams/functional areas include Shelter, WatSan, Livelihoods, PMER, GIS, Logistics/Operations, and Finance. Priority skills per team/functional area will be decided by the relevant Sector Head in charge of that team/functional area who will determine the priority skills in close coordination with the Head of Programmes. Key project management skills will include: + Ability to manage budgets + Ability to manage staff + Ability to develop and manage workplans + Ability to manage activity implementation (including logistics) + Knowledge of PMER concepts and use of data + Knowledge of GIS concepts and use of maps __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of key PRC Leyte teams/functional area staff who have improved skills in project management/PMER Denominator: # of key PRC Leyte teams/functional area staff | Pre-Test: Self assessment tool will be administered to training participants to assess their existing skills in the identified core compotencies prior to training activities. Post-Test: Self assessment tool will be administered again following training activities to training participants to assess their skills in the identified core compotencies. Participant List: Participant list for trainings on key project management skills Additional Note: This exercise will feed into personal development plans and be assessed on a yearly basis as part of performance reviews | Pre-test: Collected immediately prior to training activity Post-test: Collected immediately following training activity Participant List: Collected at the beginning of the training activity | All Sector Heads | Quarterly Report LOP Report
Shelter Training Water in emergencies training Sanitation in emergencies Volunteer and Chapter Staff Orientation to Livelihoods Programming and G-Cash PRC staff and volunteers Specialized training in LHD & G-cash GIS Trainings PASSA/PRA Training CBHFA - Training of Facilitators Manila; Training of Facilitators Tacloban, MISP Training, Epidemic Control training, Emergency Health Training, TOT for PSP | % of PASSA/PRA trained staff and volunteers who have subsequently led PASSA/PRA process in communities | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of PASSA/PRA trained PRC staff/volunteers who have led the PASSA/PRA process in communities. PRC staff and PRC volunteers trained in PASSA/PRA will include all individuals attending at least half of training days required for the PASSA/PRA process. PRC staff and PRC volunteers will be considered to have led the PASSA/PRA process in communities if they have led at least half of the trainings required for the PASSA/PRA process. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of staff/volunteers trained in PASSA/PRA who led the PASSA/PRA process in communities Denominator: # of staff/volunteers trained in PASSA/PRA | Participant List: Participant list for PASSA and PRA trainings of staff/volunteers Training Report: Training report for PASSA and PRA trainings of communities | Participant List: Collected at the beginning of the training activity Training Report: Collected immediately following training activity | Shelter Sector Head Community Mobilization Sector Head | Quarterly Report LOP Report
Conduct orientation workshops to PRC Leyte Branch and Reocvery Operation field team regarding recovery and resilience approach Conduct OD/Capacity Building Workshops Training for project staff and PRC volunteers on how to effectively implement integrated recovery and resilience programs | % of PRC staff and volunteers trained in RCRC sector modules and cross cutting approaches who demonstrate increased knowledge | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of PRC staff and volunteers trained in RCRC sector modules and cross cutting approaches who demonstrate increased knowledge. The RCRC Sector Modules included for this indicator include: + Water/Sanitation in Emergencies National Training + Sanitation in Emergencies National Training + PHAST TOT + CHAST TOT + Livelihood Training (Agriculture Replacement & Recovery Program) + Livelihood Training (STED/CMLP) + National Level Shelter Training + Branch Level Shelter Training + First Aid Training for Staff + CBHFA + DM/DRR + GIS + PMER ___________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of PRC staff and volunteers trained in RCRC Sector Modules and cross cutting approaches who demonstrate increased knowledge Denominator: # of PRC staff and volunteers trained in RCRC Sector Modules and cross cutting approaches | Pre-Test: Self assessment tool will be administered to training participants to assess their existing skills in the sector modules/cross cutting approaches prior to training activities. Post-Test: Self assessment tool will be administered again following training activities to training participants to assess their skills in the sector modules/cross cutting approaches. Participant List: Participant list for trainings on sector modules/cross cutting approaches | Pre-test: Collected immediately prior to training activity Post-test: Collected immediately following training activity Participant List: Collected at the beginning of the training activity | M&E Sector Head | Quarterly Report LOP Report
Shelter Training Water in emergencies training Sanitation in emergencies Volunteer and Chapter Staff Orientation to Livelihoods PASSA/PRA Training CBHFA - Training of Facilitators Manila; Training of Facilitators Tacloban, MISP Training, Epidemic Control training, Emergency Health Training, TOT for PSP | # of PRC staff and volunteers trained in project management/PMER | Unit of Measure: Individuals Disaggregates: Gender, Age This indicator measures the number of PRC staff and volunteers trained in project management. Project management training topics include: + Ability to manage budgets + Ability to manage staff + Ability to develop and manage workplans + Ability to manage activity implementation including logistics + Knowledge of M&E concepts and use of data + Knowledge of GIS concepts and use of maps | Participant List: Participant list for trainings on project management | Participant List: Collected at the beginning of the training activity | M&E Sector Head | Quarterly Report LOP Report
Shelter Training Water in emergencies training Sanitation in emergencies Volunteer and Chapter Staff Orientation to Livelihoods Programming and G-Cash PRC staff and volunteers Specialized training in LHD & G-cash GIS Trainings PASSA/PRA Training CBHFA - Training of Facilitators Manila; Training of Facilitators Tacloban, MISP Training, Epidemic Control training, Emergency Health Training, TOT for PSP | # of core sector trainings provided | Unit of Measure: Trainings Disaggregates: Sector This indicator measures the number of core sector trainings provided by Shelter, Livelihoods, WatSan, Health, DRR, and DP. Core sector trainings include: + Water/Sanitation in Emergencies National Training + Sanitation in Emergencies National Training + PHAST TOT + CHAST TOT + Livelihood Training (Agriculture Replacement & Recovery Program) + Livelihood Training (STED/CMLP) + National Level Shelter Training + Branch Level Shelter Training + First Aid Training for Staff + CBHFA + DM/DRR + GIS + PMER | Participant List: Participant list for trainings on sector modules/cross cutting approaches | Participant List: Collected at the beginning of the training activity | M&E Sector Head | Quarterly Report LOP Report
| # of PRC staff and volunteers participating in core sector trainings | Unit of Measure: Individuals Disaggregates: Gender, Age This indicator measures the number of PRC staff and volunteers who have participated in core sector trainings. Core sector trainings include: + Water/Sanitation in Emergencies National Training + Sanitation in Emergencies National Training + PHAST TOT + CHAST TOT + Livelihood Training (Agriculture Replacement & Recovery Program) + Livelihood Training (STED/CMLP) + National Level Shelter Training + Branch Level Shelter Training + First Aid Training for Staff + CBHFA + DM/DRR + GIS + PMER | Participant List: Participant list for trainings on sector modules/cross cutting approaches | Participant List: Collected at the beginning of the training activity | M&E Sector Head | Quarterly Report LOP Report
| % of targeted barangays that have active PRC 143 teams | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of the targeted barangays that have active 143 teams. A barangay is counted as having a 143 team if it meets the criteria defined by PRC and has officially registered the 143 team with the PRC Leyte chapter. Membership should include both BRC members and community volunteers. The 143 teams should respond to local disaters and should have members that participate in trainings and who organize/participate in PRC activities (e.g. Sanitation Day, etc). A group is considered active if they have conducted at least one meeting within the last 3 months. Note that in certain circumstances (community population limitations, etc.) it may not be necessary to have 44 members in a group in order to qualify as a 143 team. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of targeted barangay that have active PRC 143 teams Denominator: # of targeted barangay that have PRC 143 teams | CO Monthly Report: Report supplied as documentation of CO activities with 143 groups | CO Monthly Report: Collected monthly in support of CO activities in the barangay | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of targeted barangays with 143 teams | Unit of Measure: Barangay Disaggregates: None This indicator measures the number of targeted barangays with 143 teams. A barangay is counted as having a 143 team if it meets the criteria defined by PRC and has officially registered the 143 team with the PRC Leyte chapter. Membership should include both BRC members and community volunteers. | CO Monthly Report: Report supplied as documentation of CO activities with 143 groups | CO Monthly Report: Collected monthly in support of CO activities in the barangay | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of individuals trained to be part of 143 team in targeted barangays | Unit of Measure: Individuals Disaggregates: Gender, Sector This indicator measures the number of individuals trained to be part of a 143 team in a targeted barangay. Individuals should be considered trained to be part of a 143 team if they have attended at least 1 training related to 143 activities including but not limited to trainings in WatSan, Livelihoods, Shelter, Health or DRR. | Volunteer Membership List: List includes all 143 volunteers Additional Note: Tool supplied by PRC | Volunteer Membership List: Collected immediately following the 143 orientation | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of Organizational and DM capacity assessments of PRC Leyte chapter completed | Unit of Measure: Assessment Disaggregates: None This indicator measures the numer of assessment completed on Organizational and DM for the PRC Leyte chapter. The assessment is not considered complete until the assessment report has been disseminated to the PRC Leyte chapter, PRC NHQ, and other relevant stakeholders. | Assessment Report: Report supplied as documentation of the assessment of PRC Leyte Branch Organizational and DM Capacity | Assessment Report: Report supplied following assessment | Head of Programs | Quarterly Report LOP Report
| % of PRC Leyte chapter capacity development plans for DM implemented in coordination with PRC NHQ/IFRC/PNS | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of completed activities that were identified as part of Leyte chapter capacity developoment plans for DM. This implementation should occure in coordination with PRC NHQ/IFRC/PNS __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of completed activities identified as part of the Leyte chapter capacity development plans for DM Denominator: # of activites identifid as part of the Leyte chapter capacity development plans for DM | Head of Programs Monthly Report: Report supplied as documentation of coordinated implementation | Head of Programs Monthly Report: Report supplied monthly | Head of Programs | Quarterly Report LOP Report
| # of PRC staff and volunteers trained in FA/PFA | Unit of Measure: Individuals Disaggregates: Gender, Age This indicator measures the number of PRC staff and volunteers trained in FA or PFA. Individuals are not counted unless they have completed all modules of the training curriculum. | Participant List: Participant list for trainings on FA or PFA | Participant List: Collected at the beginning of the training activity | Health Sector TPA | Quarterly Report LOP Report
| % of teams/committees for WASH, Health and DRR/DP functioning within targeted barangays | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of teams/committees for WASH, Health and DRR/DP that are functioning within the targeted barangay. Committees are considered active and functioning if a majority of members participate in meetings and sector related activities. Committees should be officially registered with the government. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of teams/committees for WASH, Health, and DRR/DP that are functioning within the targeted barangay Denominator: # of teams/committees for WASH, Health, and DRR/DP within the targeted barangay | Committee Membership List: List includes all committee members for the WASH, Health, and DRR/DP | Committee Membership List: Collected immediately following the committee organization | Community Mobilization Sector Head | Quarterly Report LOP Report
| % of individuals who participated in a disaster simulation/drill in last year | Unit of Measure: Percent Disaggregates: Gender, Age This indicator measures the percentage of individuals who participated in a disaster simulation or drill in the last year. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of individuals who participated in simulation/drill in the past 12 months Denominator: # of individuals in the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the program Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the program | DRR TPA | Quarterly Report (Annual) LOP Report
| % of households with disaster preparedness plans | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of households with a written disaster preparedness plan detailing what steps the family will take to reduce their disaster risk and what actions they will take should a disaster occur. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of families with a written disaster preparedness plan Denominator: # of families in the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the program Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the program | DRR TPA | Quarterly Report (Annual) LOP Report
| % of households aware of community based early warning system | Unit of Measure: Percent Disaggregates: None This indicator measure the number of households who are aware of community based early warning systems in their community. A household is considered aware if at least one household member is aware of community based early warning systems in their community. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of househlds aware of community based early warning system Denominator: # of households in the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the program Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the program | DRR TPA | Quarterly Report (Annual) LOP Report
| # of community DRR plans developed based on assessment findings | Unit of Measure: Plans Disaggregates: None This indicators measures the number of community based DRR plans developed based on results of the CAP process. | CO Monthly Report: Report supplied as documentation of DRR plan development | CO Monthly Report: Collected monthly in support of CO activities in the barangay | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of BRC formed in the targeted communities | Unit of Measure: BRC Disaggregates: None This indicator measures the number of BRC that have been formed in the targeted communities. Only BRC with documented member lists, meeting notes, and regular meetings in line with their charter should be counted. | BRC Membership List: List includes all registered members for the BRC CO Monthly Report: Report supplied as documentation of BRC formation and activities in the targeted communities. | BRC Membership List: Collected during orientation activites CO Monthly Report: Collected monthly in support of CO activities in the barangay | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of community managed projects supported through cash grant, trainings | Unit of Measure: Projects Disaggregates: None This indicator measures the number of community projects supported through cash grants and trainings. Projects will full under the CMLP and will include only collaboratively developed livelihoods projects (e.g. cooperative to buy rice at wholesale prices and resell in the community) for which community members receive a cash grant and specific livelihood trainings. Indicator counted upon official award of cash grant. | Reconciliation Report: Report supplied as documentation of initial payment transfer to awarded association Livelihood Monthly Report: Report supplied as supporting documentation of CMLP project implementation | Reconciliation Report: Report collected quarterly Livelihood Monthly Report: Collected monthly in support of CMLP acitivies | Livelihoods TPA | Quarterly Report LOP Report
| # of community simulations and drills organized | Unit of Measure: Simulations/Drills Disaggregates: None This indicator measure the number of community simulations and drills organized and conducted as a result of program interventions. | CO Monthly Report: Report supplied as documentation of simulations and drills organized | CO Monthly Report: Report supplied as documentation of simulations and drills organized | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of capacity building trainings provided for BRC | Unit of Measure: Trainings Disaggregates: Designation This indicator measures the number of capacity building trainings provided to BRC. A training is only counted if at least 3 people from a BRC are in attendance. These trainings will include trainings in: + Local governance + Accountability and transparency + Program management + Sustainability | Participant List: Participant list for capacity building trainings CO Monthly Report: Report supplied as documentation of capacity building trainings | Participant List: Collected at the beginning of the training activity CO Monthly Report: Collected monthly in support of CO activities in the barangay | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of individuals participating in community simulation and drills | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the number of people who have participated in program facilitated community simulations and drills taking them through what to do when a disaster strikes their community. | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | DRR TPA | Quarterly Report (Annual) LOP Report
| # of individuals reached with DRR/DP messages | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the number of individuals reached with DRR/DP messages. DRR/DP messages will include those presented through awareness raising campaigns, community events, door-to-door campaigns, radio messages, etc. as well messages presented through sector trainings. | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Participant List: Participant list for sector trainings with a DRR/DP component | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project Participant List: Collected at the beginning of sector training with a DRR/DP component | DRR TPA | Quarterly Report (Annual) LOP Report
| % of individuals who are aware of shelter and settlement related risks | Unit of Measure: Percent Disaggregates: Gender, Age This indicator measures the percent of individuals who are aware of shelter and settlement related risks. Individuals will be made aware of shelter related risk through the PASSA/PRA process, Safe Shelter Techniques Orientation, and Habitability Orientation and Awareness Campaigns. Individuals will be considered aware if they can positive identify at least 70% of the key messages from these interventions. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of people who are aware about shelter and settlement related risk Denominator: # of people in catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | Shelter Sector Head | Quarterly Report (Annual) LOP Report
| % of individuals who participated in a Shelter, Livelihoods, WatSan, Health, DRR/DP skills development training who have an increased knowledge on the subject covered | Unit of Measure: Percent Disaggregates: Gender, Age This indicator measures the percent of individuals who have participated in Shelter, Livelihoods, WatSan, Health, DRR/DP skills development and who have increased knowledge on the subjects covered in the skills developement trainings. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of community members/volunteers who participated in Shelter, Livelihoods, WatSan, Health, DRR & DP skills development who have increased knowledge on the subject covered Denominator:# of community members/volunteers who participated in Shelter, Livelihoods, WatSan, Health, DRR & DP skills development | Pre-Test: Self assessment tool will be administered to training participants to assess their existing skills prior to training activities. Post-Test: Self assessment tool will be administered again following training activities to training participants to assess their skills. Participant List: Participant list for trainings on sector | Pre-test: Collected immediately prior to training activity Post-test: Collected immediately following training activity Participant List: Collected at the beginning of the training activity | All Sector Heads | Quarterly Report LOP Report
| # of community action plans prepared as a result of the PASSA/PRA process | Unit of Measure: Plans Disaggregates: None This indicator measures the number of communities that have participated in the PASSA/PRA process and subsequently developed a CAP based on participatory exercises. | CAP Reports: Report supplied as documentation of the PASSA/PRA process and completion of CAP | CAP Reports: Report supplied following the PASSA/PRA process and compilation of CAP | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of individuals who have participated in the PASSA/PRA process | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the number of community members in targeted barangays who attended meetings or participated in activities during their community's PASSA (Steps 1-4) and PRA process. | CAP Reports: Report supplied as documentation of the PASSA/PRA process Participant List: Participant list for PASSA/PRA process | CAP Reports: Report supplied following the PASSA/PRA process Participant List: Collected at the beginning of the PASSA/PRA process | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of individuals trained in livelihood activities | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the number of community members trained in livelihood activities through the program. Livelihood activities will include the Agriculture Replacement & Recovery Program, STED, and CMLP. | Participant List: Participant list for livelihood training activities Training Report: Training report for livelihood training activities | Participant List: Collected at the beginning of the training activity Training Report: Report supplied following the completion of the training activity | Livelihoods TPA | Quarterly Report LOP Report
| # of individuals trained in DRR/DP | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the number of individuals trained in DRR/DP. Trained individuals will include those who receive DRR/DP specific trainings and will also include individuals who participate in sector trainings that have a significant DRR/DP component. | Participant List: Participant list for DRR/DP training activities Training Report: Training report for DRR/DP training activities | Participant List: Collected at the beginning of the training activity Training Report: Report supplied following the completion of the training activity | DRR TPA | Quarterly Report LOP Report
| # of individuals trained in health services | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the number of community members trained in health services. Trainings in health services will include the following subjects: + CBHFA + PSP + Epidemic Control + Emergency Health | Participant List: Participant list for health services training activities Training Report: Training report for health services training activities | Participant List: Collected at the beginning of the training activity Training Report: Report supplied following the completion of the training activity | Health TPA | Quarterly Report LOP Report
| # of BHW/BNS trained in technical topics and FA based on training needs assessments | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the number of BHW and BNS who are trained in technical topics and FA. Trainings will be tailored based on an initial needs assessment. | Participant List: Participant list for technical topics and FA training activities Training Report: Training report for technical topics and FA training activities | Participant List: Collected at the beginning of the training activity Training Report: Report supplied following the completion of the training activity | Health TPA | Quarterly Report LOP Report
| % of households who received shelter repair or retrofitting assistance using safe shelter practices at their house | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of households that have received shelter repair or retrofitting assistance that are using safe shelter practices at their house. Safe shelter practices will be based on the 8 build back safer key messages and based on their SRA proposal. Each beneficiary household is oriented in 8 build back key messages before receiving funds and materials given by the SRA program, so they are intended to rehabilitate their houses in line with these techniques. This result will be assessed by post construction monitoring by ARC/PRC shelter team. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of households who received shelter repair or retrofitting assistance implementing safe shelter practices at their house Denominator: # of households who received shelter repair or retrofitting assistance | Post Construction Monitoring Tool: Post construction monitoring tool will be used to collect the data points necessary to determine the use of SRA funds towards safer shelter construction. Additional Note: Tool supplied by PRC | Post Construction Monitoring Tool: Collected following the distribution of funds | Shelter Sector Head | Quarterly Report LOP Report
| % of households who improved/repaired their shelter after handover with their own resources | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of households that have improved/repaired their shelter after handover with their own resources. Resources should include monetary and non-monetary resources. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of households who have received shelter repair or retrofit kits who have improved/repaired their shelter with their own resources Denominator: # of households who have received shelter repair or retrofit kits | Post Construction Monitoring Tool: Post construction monitoring tool will be used to collect the data points necessary to determine the use of household funds towards safer shelter construction. Additional Note: Tool supplied by PRC | Post Construction Monitoring Tool: Collected following the distribution of funds | Shelter Sector Head | Quarterly Report LOP Report
| % of individuals aware about safe disposal of household solid waste | Unit of Measure: Percent Disaggregates: Gender This indicator measures the percentage of community members that are aware of safe disposal of household soild waster as a result of the program. People are considered to be aware if they have knowledge of at least one safe disposal message on separation of waste, recycling practices, reuse practices, propering composting practices, etc. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of people aware of safe disposal of household solid waste Denominator: # of people in the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | WatSan TPA | Quarterly Report LOP Report
| % of individuals aware about safe health or hygiene practices | Unit of Measure: Percent Disaggregates: Gender This indicator measures the percentage of people aware of safe health or hygiene practices as a result of the program. People are considered to be aware if they have knowledge of at least one safe health and hygiene messages on handwashing practices, safe water storage, safe food preparation, safe water collection, latrine usage, etc. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of people aware of safe health of hygiene practices Denominator: # of people in the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | WatSan TPA | Quarterly Report (Annual) LOP Report
| % of households with safer and healthier practices to reduce risk of hazards | Unit of Measure: Percent Disaggregates: None This indicator measures the percent of households exhibiting safer and healthier practices to reduce risk of hazards. Practices considered to be safer and healthier include the use of safe water sources, safe waste disposal practices, use of mosquito nets, use of light colored walls for vector transmission reduction, etc. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of households exhibiting safer and healthier practices to reduce risk of hazards Denominator: # of households in the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | DRR TPA | Quarterly Report (Annual) LOP Report
| % of houses with screens on windows to prevent mosquito entry | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of homes with screens (without large holes) on all windows. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of households with screens on windows to prevent mosquito entry Denominator: # of households in the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | Shelter TPA (Engineer) DRR TPA | Quarterly Report (Annual) LOP Report
| # of household members who participated in the construction process | Unit of Measure: Households Disaggregates: None This indicator measures the number of household members who participated in the construction process. It is expected that at least one member of every household with shelter support will participate in the construction process. | Participant List: Participant list for construction activities | Participant List: Collected at the beginning of the construction activity | Shelter TPA (Engineer) | Quarterly Report LOP Report
| # of household members who received orientation on safe shelter techniques | Unit of Measure: Households Disaggregates: None This indicator measures the number of households members who have received orientation on safe shelter techniques. It is expected that at least one member of every household receiving shelter support will also receive an orientation on safe construction as part of the Safe Shelter Techniques Orientation. | Participant List: Participant list for Safe Shelter Techniques Orientation training | Participant List: Collected at the beginning of each Safe Shelter Techniques Orientation training | Shelter TPA (Engineer) | Quarterly Report LOP Report
| # of households assisted towards increased security of land tenure | Unit of Measure: Households Disaggregates: None This indicator measures the number of households assisted towards increased security of tenure. This will include households that have received paralegal services as a result of the program as well as households that have recieved other program interventions that help strengthen security of tenure. | Participant List: Participant list for paralegal services | Participant List: Collected at the beginning of each provision of paralegal services | Shelter Sector Head | Quarterly Report LOP Report
| # of community action plans updated after PHAST implementation | Unit of Measure: Plans Disaggregates: None This indicator measures the number of CAP updated after PHAST implementation. After completion of the PHAST module, the CAP should be updated and a handover cetificate provided. Revision needs to be included in the PHAST plan of activities in order to ensure ease of revision. | CAP Reports: Report supplied as documentation of the revision process | CAP Reports: Report supplied immediately following the revision process | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of individuals participating in PHAST activities | Unit of Measure: People Disaggregates: Gender This indicator measures the number of individuals participating in PHAST activities. Individuals should includes BAWASA members, community volunteers and other community members. This indicator should includes all community members who attend activities detailed in the PHAST Action Plan. Individuals included if they have attended all 7 modules. | PHAST Volunteer Record Book: Participant list for PHAST training activities Additional Note: Tool supplied by PRC | PHAST Volunteer Record Book: Collected at the beginning of each of the PHAST steps | WatSan TPA | Monthly Report Quarterly Report LOP Report
| # of individuals reached by health/hygiene promotion activities | Unit of Measure: Individuals Disaggregates: Gender This indicator measures the number of individuals reached by health/hygiene promotion activities. Health/Hygiene promotion activities will include door-to-door community awareness raising campaigns, community events, posters, radio broadcasts, etc on topics such as handwashing, dengue, shistosomiasis, vector control, latrine use, safe water collection and storage, etc | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. WatSan Monthly Report: Report supplied as documentation of health/hygiene promotion activities | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project WatSan Monthly Report: Report supplied monhtly | WatSan Sector Head | Quarterly Report LOP Report
| # of schools selected for CHAST | Unit of Meassure: Schools Disaggregates: None This indicator measures the number of schools selected for participation in CHAST based on CAP needs identification | Inception Report: Report includes a list of selected schools WatSan Monthly Report: Report supplied as documentation of CHAST selection activities | Inception Report: Supplied immediately following initial assessment of needs/gaps WatSan Monthly Report: Report supplied monthly | WatSan Sector Head Health TPA | Quarterly Report LOP Report
| # of school WASH facilities built/repaired/improved | Unit of Measure: Facilities Disaggregates: Type This indicator measures the number of school WASH facilities built/repaired/improved as a results of the program. Wash facilities to be built/repaired/improved should be identified through the CAP and CHAST process. | Inception Report: Report includes a list of selected schools WatSan Monthly Report: Report supplied as documentation of CHAST selection activities CHAST Monitoring Tool: Report supplied as documentation of CHAST activities Additional Note: Tool supplied by PRC | Inception Report: Supplied immediately following initial assessment of needs/gaps WatSan Monthly Report: Report supplied monthly CHAST Monitoring Tool Report supplied immediately following the completion of CHAST activities | WatSan Sector Head Health TPA | Quarterly Report LOP Report
| # of students reached with child hygiene and sanitation transformation | Unit of Measure: Individuals Disaggregates: Topic This indicator refers to the total number of students reached with hygiene and sanitation promotion using the child hygiene and sanitation transformation (CHAST) methodology. Students are considered as having been reached if they have participated in all steps. Note: MWRS Indicator Definition | CHAST Volunteer Record Book: Participant list for CHAST training activities Additional Note: Tool supplied by PRC | CHAST Volunteer Record Book: Collected at the beginning of each of the CHAST steps | WatSan TPA | Quarterly Report LOP Report
| % of households have increased income as a result of support received by program activities | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of households that haved participated in CCG, STED, Agricultural Replacement & Recovery Program, or CMLP that report increased average monthly income. Income will be self reported and be measured as average monthly earnings over the previous __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of households that have participated in CCG, STED, Agricultural Replacement & Recovery Program, and CMLP that report increased monthly income Denominator: # of households that have participated in CCG, STED, Agricultural Replacement & Recovery Program, and CMLP | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | Livelihoods TPA | Quarterly Report LOP Report
| # of households that have been provided with livelihood support grants | Unit of Measure: Households Disaggregates: None This indicator refers to the total number of households that have received conditional cash grants after their individual proposals to support their livelihood was received and approved through a community selection process. The proposals are submitted by individuals to support the start-up of an alternative means of livelihood, enhance previous livelihood assets (e.g. boats, nets, quick growing seeds, replacement tools, fertilizer, etc.) or inputs to diversify income sources (such as small-scale agriculture, animal husbandry, tailoring or other income generation activities). Note: MWRS Indicator Defintion | GCash Reconciliation Report: Report supplied as documentation of initial payment transfer to households | GCash Reconciliation Report: Report collected quarterly | Livelihoods TPA | Monthly Report Quarterly Report LOP Report
| # of individuals provided with marketable livelihood activities training | Unit of Measure: People Disaggregates: None This indicator measures the number of people provided with marketable livelihood activities training. This will generally include participants in the Agricultural Extension program, SME Development and Community based programs who have been trained in livelihoods topics such as marketing plan development for their business, agircultural techiques, financial management, market assessments, etc. | Participant List: Participant list for livelihood activities trainings | Participant List: Collected at the beginning of each livelihood activities training | Livelihoods TPA | Quarterly Report LOP Report
| # of individuals/enterprises given financial support | Unit of Measure: STED/CMLP Disaggregates: None This indicator measures the number of individuals participating in STED and CMLP activities that have been given financial support. Financial support will be based on business development plans/proposals and will be dispersed in the form of grants and supplies. Individuals will be counted upon first distribution of grant, supplies, etc. | GCash Reconciliation Report: Report supplied as documentation of initial payment transfer to households Livelihood Monthly Report: Report supplied as additional documentation of business development plan/proposals STED/CMLP Proposal: Report supplied as additional documentation of proposal | GCash Reconciliation Report: Report collected quarterly Livelihood Monthly Report: Report supplied monthly STED/CMLP Proposal: Report supplied upon completion of proposal selection process | Livelihoods TPA | Quarterly Report LOP Report
| # of individuals supported to develop business/marketing plan | Unit of Measure: Individuals Disaggregates: None This indicator measures the number of individuals participating in STED and CMLP activities that have been trained and mentored by ARC/PRC staff to develop business/marketing plans for their business. Individuals must have received at least one training from ARC/PRC | Participant List: Participant list for livelihood activities trainings Livelihood Monthly Report: Report supplied as additional documentation of business development plan/proposals | Participant List: Participants collected at the begin of the training activitiy Livelihood Monthly Report: Report supplied monthly | Livelihoods TPA | Quarterly Report LOP Report
| # of carpenters and craftspeople trained in shelter construction | Unit of Measure: People Disaggregates: None This includes all skilled labour, carpenters, and craftspeople who have been trained in shelter construction techniques. This indicator should only include individuals that have completed the course and received certification of their skills. Note: MWRS Indicator Definition | Copy of Course Completion Certificate: Course completion certificate should be copied and stored Shelter Monthly Report: Report supplied as documentation of completion of certification program | Copy of Course Completion Certificate: Course completion certificate should be collected upon completion of course by beneficiary Shelter Monthly Report: Report supplied monthly | Shelter Sector Head Livelihood TPA | Quarterly Report LOP Report
| # of households provided with conditional financial support for asset replacement/agricultural recovery | Unit of Measure: Households Disaggregates:None This indicator measures the number of houeholds that have received a CCG through the Agricultural Asset Replacement & Recovery Program intended for replacement of assets lost during Typhoon Haiyan. Households must have documentation of the lost asset and will receive the cash grant on the condition that the grant be used for the purpose of replacing this asset. | GCash Reconciliation Report: Report supplied as documentation of initial payment transfer to households Livelihood Monthly Report: Report supplied as additional documentation of business development plan/proposals | GCash Reconciliation Report: Report supplied as documentation of initial payment transfer to households Livelihood Monthly Report: Report supplied as additional documentation of business development plan/proposals | Livelihoods TPA | Quarterly Report LOP Report
| % of community water and sanitation committees regularly collecting fees in order to maintain facilities for users | Unit of Measure: Percent Disaggregates: This indicator measures the percent of BAWASA that are regularly (in the last three months) collecting fees in order to maintain facilities for users. Collection of fees for WASH facilities should align with guidelines in O&M training. The types of interventions requiring the collection of fees (communal water points, etc) are outlined the O&M Manual. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of facilities repaired by community water and sanitation committee with their own resources Denominator: # of facilities repaired by community water and sanitation committee | Baseline Survey (WatSan Committee): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (WatSan Committee): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (WatSan Committee): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (WatSan Committee): Administered at the beginning stage of the project Annual Survey (WatSan Committee): Administered a year following the baseline survey. Endline Survey (WatSan Committee): Administered in the final stage of the project | WatSan TPA | Quarterly Report LOP Report
| % of facilities repaired by community water and sanitation committee with their resources | Unit of Measure: Percent Disaggregates: This indicator measures the percentage of facilities repaired by BAWASA using fees collected specifically for that purpose. Fees will be generally be collected for the repair of a water point or other WASH intervention. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of facilities repaired by community water and sanitation committee with their own resources Denominator: # of facilities repaired by community water and sanitation committee | Baseline Survey (WatSan Committee): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (WatSan Committee): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (WatSan Committee): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (WatSan Committee): Administered at the beginning stage of the project Annual Survey (WatSan Committee): Administered a year following the baseline survey. Endline Survey (WatSan Committee): Administered in the final stage of the project | WatSan TPA Community Mobilization TPA | Quarterly Report (Annual) LOP Report
| % of households in targeted barangays with safer houses | Unit of Measure: Percent Disaggregates: This indicator meaures the percentage of households in targeted barangay that have safer houses. This indicator will assume that all core households are safer than previoius housing. Households receiving SRA intervention will receive an indexed damage score prior to SRA fund distribution. The households will then receive an indexed damage score follow the distribution based on the same criteria of the initial damage score. Households are considered to be safer if the indexed damage score is lower than before the SRA fund distribution. | Post Construction Monitoring Tool: Post construction monitoring tool will be used to collect the data points necessary to determine the use of household funds towards safer shelter construction. Additional Note: Tool supplied by PRC | Post Construction Monitoring Tool: Collected following the distribution of funds | Shelter Sector Head | Quarterly Report LOP Report
| % of community action plans completed | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of community action plans that have been completed. A community action plan will be considered complete when at least five activities that were outlined have been completed. | CAP Reports: Report supplied as documentation of the process | CAP Reports: Report supplied immediately following the revision process | Community Mobilization Sector Head | Quarterly Report LOP Report
| # of households provided with a core shelter | Unit of Measure: Households Disaggregates: Barangay This indicator refers to the total number of households provided with a core shelter (i.e. wood and half-concrete model and other types) provided by the program. Households should only be counted submission of the final completion report. Note: MWRS Indicator Defintion | Final Completion Report: Report supplied and signed as documentation of completion of construction Certificate of Occupancy: Certificate will supplement the Final Completion Report and provide additional documentation of completion of construction Shelter Monthly Report: Report supplied as additional documentation of construction | Final Completion Report: Report supplied upon successful completion of construction Certificate of Occupancy: Certificate supplied upon successful completion of construction Shelter Monthly Report: Report collected monthly | Shelter TPA (Engineer) | Monthly Report Quarterly Report LOP Report
| # of households provided with shelter repair or retrofitting assistance | Unit of Measure: Households Disaggregates:Barangay This indicator refers to the total number of households that have completed the shelter repair [or retrofitting] assistance process with the 1st and/or 2nd cash grant amounting to a total of PHP 10,000 and corrugated galvanized iron sheets, or at least one of these. This numbers includes households that received cash grants which were later discontinued due to violation of agreement. Note: FWRS Indicator Defintion | GCash Reconciliation Report: Report supplied as documentation of initial payment transfer to households | GCash Reconciliation Report: Report supplied as documentation of initial payment transfer to households | Shelter TPA (Engineer) | Monthly Report Quarterly Report LOP Report
| # of households relocated and provided with a shelter solution | Unit of Measure: Households Disaggregates:Barangay This indicator refers to the total number of households that have been relocated to identified and approved relocation sites and given a house to live in. Households should only be counted submission of the final completion report. Note: MWRS Indicator Defintion | Final Completion Report: Report supplied and signed as documentation of completion of construction Certificate of Occupancy: Certificate will supplement the Final Completion Report and provide additional documentation of completion of construction Shelter Monthly Report: Report supplied as additional documentation of construction | Final Completion Report: Report supplied upon successful completion of construction Certificate of Occupancy: Certificate supplied upon successful completion of construction Shelter Monthly Report: Report collected monthly | Shelter TPA (Engineer) | Monthly Report Quarterly Report LOP Report
| # of households with new santiation facilites | Unit of Measure: Households Disaggregates: Barangay This indicator measures the number of household that have newly contructed sanitation facilities. This could include facilities associated with core or SRA interventions. | Final Completion Report: Report supplied and signed as documentation of completion of construction Certificate of Occupancy: Certificate will supplement the Final Completion Report and provide additional documentation of completion of construction Shelter Monthly Report: Report supplied as additional documentation of construction | Final Completion Report: Report supplied upon successful completion of construction Certificate of Occupancy: Certificate supplied upon successful completion of construction Shelter Monthly Report: Report collected monthly | Shelter TPA (Engineer) Shelter TPA (WatSan Engineer) | Monthly Report Quarterly Report LOP Report
| # of households with repaired/improved santitation facilties | Unit of Measure: Households Disaggregates:Barangay This indicator measures the number of households with repaired/improved sanitation facilities as a result of the program. This should include repaired/improved sanitation facilities associated with the SRA interventions. | Post Construction Monitoring Tool: Post construction monitoring tool will be used to collect the data points necessary to determine the use of household funds towards safer shelter construction. Additional Note: Tool supplied by PRC | Post Construction Monitoring Tool: Collected following the distribution of funds | Shelter TPA (Engineer) Shelter TPA (WatSan Engineer) | Monthly Report Quarterly Report LOP Report
| # of households with new santiation facilities in relocation site | Unit of Measure: Households Disaggregates: Barangay This indicator measures the number of household that have newly contructed sanitation facilities in a relocation site. | Final Completion Report: Report supplied and signed as documentation of completion of construction Certificate of Occupancy: Certificate will supplement the Final Completion Report and provide additional documentation of completion of construction Shelter Monthly Report: Report supplied as additional documentation of construction | Final Completion Report: Report supplied upon successful completion of construction Certificate of Occupancy: Certificate supplied upon successful completion of construction Shelter Monthly Report: Report collected monthly | Shelter TPA (Engineer) | Monthly Report Quarterly Report LOP Report
| # of barangay with completed household profiles | Unit of Measure: Barangay Disaggregates: None This indicator measures the number of barangay that have completed houshold profiling data. Profiles should not be considered completed until analysis has been completed for core and SRA classification of beneficiaries within the barangay. | Household Profiling Table: Cleaned and formatted table supplied as documentation of completion | Household Profiling Table: Data collected at the beginning of project | M&E Sector Head | Quarterly Report LOP Report
| % of households who report improved access to health services in the barangay | Unit of Measure: Percent Disaggregates: None This indicator measures the number of households who report having improved access to health services in their barangay. Household access is considered to be improved if the household responds positively to an increase in the availability of services, an increase in quality of services, or a decrease in travel time to the nearest health facility as a result of the project. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of households who report having improved access to health services Denominator: # of households within the catchment area | Baseline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Annual Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. Endline Survey (Household): Survey will be administered to a representative sample of the target population. Survey will provide data points necessary to calculate indicator. | Baseline Survey (Household): Administered at the beginning stage of the project Annual Survey (Household): Administered a year following the baseline survey. Endline Survey (Household): Administered in the final stage of the project | Health TPA | Quarterly Report (Annual) LOP Report
| % of water systems tested whose water quality meets the criteria as per national standard | Unit of Measure: Percent Disaggregates: None This indicator measures the percentage of water systems whose water quality meets the criteria as per the national standards. This indicator is calculated for water points that ARC/PRC is constructing/repairing only. __________ Indicator will be calculated with the numerator and denominator defined as: Numerator: # of water points that the program is constructing/repairing that meet the national standard Denominator: # of water points that the program is constructing or repairing | Field Testing Results Table: Table includes the water quality results for PH, Conductivity, Turbidity, TDS, Salinity Laboratory Results Table: Table includes the water quality results for bacterial testing WatSan Monthly Report: Report supplied as documentation of water points constructed/repaired | Field Testing Results Table: Table constructed as tests results are generated Laboratory Results Table: Table constructed as tests results are generated WatSan Monthly Report: Report collected monthly | WatSan TPA | Quarterly Report LOP Report
| # of community infrastructure facilities, excluding water and sanitation facilities, repaired/constructed | Unit of Measure: Facilities Disaggregates: None This indicator measures the number of community infrastructure facilities identified as a CAP priority, such as health facilities/schools/public places, that have been repaired or constructed. This indicator should not include water and sanitation facilities. | Final Completion Report: Report supplied and signed as documentation of completion of construction Shelter Monthly Report: Report supplied as additional documentation of construction | Final Completion Report: Report supplied upon successful completion of construction Shelter Monthly Report: Report collected monthly | Shelter TPA (Engineer) | Monthly Report Quarterly Report LOP Report
| # of community water and sanitation facilities repaired/constructed | Unit of Measure: Facilities Disaggregates: None This indicator measures the number of community water and sanitation faciliites provided with repaired or constructed water and sanitation facilities. WASH community works such as health facilities/schools/public places and as identified based on CAP priorities repaired or reconstructed. | Final Completion Report: Report supplied and signed as documentation of completion of construction WatSan Monthly Report: Report supplied as additional documentation of construction | Final Completion Report: Report supplied upon successful completion of construction WatSan Monthly Report: Report collected monthly | Shelter TPA (Engineer) Shelter TPA (WatSan Engineer) | Monthly Report Quarterly Report LOP Report
| # of mitigation projects completed to reduce hazards in the targeted communities | Unit of Measure: Projects Disaggregates: None This indicator measures the number of mitigation projects completed to reduce hazards in the targeted communities. Mitigation projects should be based on the hazards identified in the CAP process. | Final Completion Report: Report supplied and signed as documentation of completion of project implementation CO Monthly Report: Report supplied as additional documentation of project implementation | Final Completion Report: Report supplied upon successful completion of project implementation CO Monthly Report: Report collected monthly | DRR TPA | Monthly Report Quarterly Report LOP Report
| # of health facilities re-equipped with basic equipment | Unit of Measure: Facilities Disaggregates: None This indicator measures the number of health facilities that have been provided with at least one piece of health equipment (BP machine, weighing scale, etc) as a result of the program. Equipment supplied will be based on a needs-assessment. | Final Completion Report: Report supplied and signed as documentation of re-equipment. Report should include receipts of purchases. Health Monthly Reports: Report supplied as documentation of the equipment supplied | Final Completion Report: Report supplied upon completion of facilities re-equipment Health Monthly Reports: Report collected montly | Health TPA | Quarterly Report LOP Report
| # of rehabilitated/retrofitted spaces identified as emergency evacuation spaces | Unit of Measure: Buildings Disaggregates: None This indicator measures the number of spaces identified as emergency evacuation spaces that have been rehabilitated or retrofitted as a result of the program. Rehabilitated or retrofitted spaces will include community works (i.e. schools, etc.) that have been identified as CAP priorities. The spaces must be rehabilitated or retrofitted to a generally accepted level of safety for their intended us. Spaces must also be designated as an emergency evacuation center with the BRC. | Final Completion Report: Report supplied and signed as documentation of completion of construction Shelter Monthly Report: Report supplied as additional documentation of construction | Final Completion Report: Report supplied upon successful completion of construction Shelter Monthly Report: Report collected monthly | Shelter TPA (Engineer) Shelter TPA (WatSan Engineer) | Monthly Report Quarterly Report LOP Report
| Estimated total # of people reached by RCRC services | Unit of Measure: People Disaggregates: Gender, Age This indicator measures the estimated total number of people reached by RCRC services. A person is considered to be reached if they have received a significant and meaningful intervention as a result of the program. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will serve as documetation of figures calculated from TTL database. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will be supplied monthly | M&E Sector Head | Monthly Report Quarterly Report LOP Report
| # of households reached by program | Unit of Measure: Households Disaggregates: None This indicator measures the number households reached by program interventions. Houeholds reached will include all households who have received inputs, activities or services directly from the program including households that have at least one member who has participated in activities/trainings/home visits, accessed services provided, or received materials/messages or information intended to improve knowledge and behaviors. Houeholds reacehd may also include households with members benefitting from resilience projects if we can demonstrate they are actively accessing a service (e.g. a water point, latrine usage). | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will serve as documetation of figures calculated from TTL database. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will be supplied monthly | M&E Sector Head | Monthly Report Quarterly Report LOP Report
| # of households provided with safe shelter solutions | Unit of Measure: Households Disaggregates: None This indicator measure the number of households or families that have been provided with safe shelter solution. This indicator will include households that have received core, SRA, and relocation housing interventions. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will serve as documetation of figures calculated from TTL database. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will be supplied monthly | M&E Sector Head | Monthly Report Quarterly Report LOP Report
| # of community members who received training through program interventions | Unit of Measure: People Disaggregates: Gender, Age This indicator mesaures the number of individuals who have received at least one training on program interventions. Community members will include any individuals within the program activity catchment area that have received at least one training as a part of a program interventions. Trainings will include any structured group or individual training with clearly defined goals and objectives. Program interventions include all interventions promoted by the program, including but not limited to Shelter, WatSan, Livelihood, DRR, Health, DM, and DP interventions. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will serve as documetation of figures calculated from TTL database. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will be supplied monthly | M&E Sector Head | Monthly Report Quarterly Report LOP Report
| # of staff and volunteers received training | Unit of Measure: People Disaggregates: Gender, Age This indicator measure the number of PRC staff and volunteers that have received trainings as a result of the program. Trainings will include any structured group or individual training with clearly defined goals and objectives. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will serve as documetation of figures calculated from TTL database. | Database Table: Database table compiled from intervention tables to determine extent of overlap of intervention activities. M&E Monthly Report: Report will be supplied monthly | M&E Sector Head | Monthly Report Quarterly Report LOP Report
| # of barangay reached by program | Unit of Measure: Barangay Disaggregates: None This indicator measures the number of barangay that have been reached by the program. A barangay is considered to be reached if a majority of households within the barangay have received significant and meaningful interventions as a result of the program. | M&E Monthly Report: Report will serve as documetation of figures calculated from TTL database. | M&E Monthly Report: Report will be supplied monthly | M&E Sector Head | Monthly Report Quarterly Report LOP Report
Acronyms
ARC: American Red Cross BAWASA: Barangay Water and Sanitation Committee BHW: Barangay Health Worker BNS: Barangay Nutritional Scholar BRC: Barangay Recovery Committee CAP: Community Action Plan CBHFA: Community Based Health and First Aid CCG: Conditional Cash Grant CHAST: Child Hygiene and Sanitation Training CMLP: Community Managed Livelihood Program CO: Community Organizer DM: Disaster Management DP: Disaster Preparedness DRR: Disaster Risk Reduction FA: First Aid GIS: Geographic Information Systems HQ: Headquarters IFRC: International Federation of Red Cross and Red Crescent Societies LOP: Life of Project M&E: Monitoring and Evaluation NHQ: National Headquarters PASSA: Participatory Approach to Safe Shelter Awareness PFA: Psychosocial First Aid PHAST: Participatory Hygiene and Sanitation Transformation PMER: Planning, Monitoring, Evaluation, and Reporting PNS: Partner National Society PRA: Participatory Rural Appraisal PRC: Philippines Red Cross PSP: Psychosocial Support Program RC: Red Cross RCRC: Red Cross Red Crescent SME: Small and Medium Enterprises SRA: Shelter Repair and Retrofitting Assistance STED: Skill Training and Enterprise Development TTL: TOT: Training of Trainers WASH: Water, Sanitation, and Hygiene WatSan: Water and Sanitation
Note on B5: William McFall: Should change the wording from staff and volunteers to only staff to alligned with indicator 1. Should also change project management to project management/PMER
Note on B6: William McFall: Change the wording to reflect the relationship wiith indicator three and the following indicator
Note on C20: William McFall: DRR projects not CMLP
Note on C22: William McFall: Remove training subjects
Note on C24: William McFall: What are the DRR/DP messages
Note on B25: William McFall: Would like to reword the indicator to incorporate more than just risk
Note on C35: William McFall: Need to more clearly define messages
Note on C38: William McFall: What is a large hole?
Note on C39: William McFall: Are we specifically interesed in number of family members?
Note on B49: William McFall: rename
Note on B54: William McFall: CCG not intended for asset replacement, need to change indicator to Ag Recovery Program
Note on C67: William McFall: Need to more completely define national standards
Note on D67: William McFall: need lab test results
Note on E67: William McFall: need lab test results
Note on C69: William McFall: may need to define what facilites are (handpumps, wells ?)
Note on C70: William McFall: Should clarify mitigation projects

## Logframe Changes Documentation (hidden)
Original | Updated | Notes
% of key PRC Leyte teams/functional areas whose staff have improved skills in project management/PMER | % of key PRC Leyte teams/functional areas whose staff have improved skills in project management/PMER
% of PASSA trained staff/volunteers led PASSA process in communities | % of PASSA/PRA trained staff/volunteers led PASSA/PRA process in communities | PASSA only paritially applied with PRA techniques used after step 4.
% of targeted communites that have an PRC 143 teams | % of targeted barangays that have an PRC 143 teams | More specific
PRC Leyte branch have improved capacity to respond to disasters (qualitative) | Deleted | Not an indicator
% of targeted barangays that have PRC 143 teams | % of targeted barangays that have active PRC 143 teams
Organizational and DM Capacity assessment of PRC Leyte Branch completed (qualitative)
Branch’s Capacity Development Plans for DM implemented in coordination PRCNHQ/IFRC/PNS (qualitative) | % of Branch’s Capacity Development Plans for DM implemented in coordination PRCNHQ/IFRC/PNS
Improve volunteer mobilization system including database in PRC Leyte Branch (Qualitative) | Deleted | Activity - not indicator
% of active teams/committees for WASH , Health and DRR/DP functioning within targeted communities | % of teams/committees for WASH , Health and DRR/DP functioning within targeted barangays | numerator and denominator were the same
% of family with disaster preparedness plans | % of households with disaster preparedness plans | Households rather than families for consistency
% of HHs aware about community based early warning system | % of households aware of community based early warning system | wording
% of community member who participated in PASSA is aware about shelter related risk. | % of community members who participated in PASSA/PRA are aware about shelter related risk. | PASSA to PASSA/PRA; wording
% of community member who participated in PASSA is aware about shelter related risk. | % of community members who are aware about shelter related risk. | This should be all community members participating in the shelter validation process (approximately 90% of target population)
# of community members trained in PHAST | Deleted | Community members participate in PHAST they are not trained in it. Staff/Volunteers are trained in the TOT. Moved to objective 1 under staff trainings.
# of community action plan prepared as a result of adapted PASSA | # of community action plan prepared as a result of adapted PASSA/PRA | PASSA/PRA
# of new stores in targeted communities registered as Gcash Agents | Deleted | Not in the project plan
% of HH/SME have increased and sustained income as a result of support received by program activities | % of HH/SME have increased income as a result of support received by program activities | Can't measure sustained
# of HH that receive GCash Mobile Money | # of HH that receive GCash Money | terminology change
People report that their community is more safer and resilient (qualitative) | Deleted | Not measureable
% of barangay members who report improved access to health services in the barangay | % of households who report improved access to health services in the barangay

## WASH Casual Pathway (hidden)
Activities | Outputs | Indicators - WASH | Outcome | Outcome Indicators - WASH | Objective | Impact
Objective 1.
Harmonization of participatory tools (VCA, CBHFA, PHAST, PASSA and others relevant) and training for key staff and volunteers on harmonized approach and tools (TT.B) | 1.1.1 PRC staff and volunteers trained and mentored in project management, core community implementation sectors and cross cutting approaches | # of core sector trainings provided # of PRC staff who participate in corse sector trainings | 1.1 PRC HQ and Leyte Branch have increased capacity to implement integrated recovery program | % of PRC staff and volunteers trainedin RCRC Sector modules and cross cutting approached who demonstrate increased knowledge | 1. Increase PRC capacity in community based recovery and preparednes to enhance community resilience over a 3 year period | Safer, More Resilient Communities
Water-in-emergencies Training (TT.B)
Sanitation-in-emergencies Training (TT.B)
| 1.2.1 143 Volunteers available in each Barangary across the program areas | # targeted barangays with 143 teams # of community members trained to be part of 143 teams in targeted barangays | 1.2 PRC Leyte branch and targeted communities have active network of RC volunteers | % of targeted communities that have a PRC 143 team
| 1.2.2. PRC Leyte branch capacity to respond to disastered enhanced | Organizal and DM Capacity Assessment Completed Branch Capacity Development Plans for DM implemented Improved volunteer mobilization systems (including Leyte Branch database)
|  |  | 2.1 Targeted communities are organized and have improved disaster safety and resilience | % of active teams/committees for WASH, Health and DRR/DP functioning within targeted communities | 2. To increase community capacity to adopt resilient practices
TOT PHAST (TT.B) | 2.2.1 Community members are trained in topic of project intervention | # of community members trained in PHAST | 2.2 Community members have increased knowledge and skills to support their recovery and resilience | % of community members/volunteers who participated in shelter (PASSA), livelihoods, WASH (PHAST), health, DRR & DP skills development has increased knowledge on skills covered
Training for facilitators PHAST (TT.C)
Implementation sessions PHAST (TT.E)
TOT WatSan in schools (TT.B)
Training for facilitators for WatSan in schools (TT.C)
Implementation sessions WatSan in schools (TT.E)
Develop IEC Materials | 2.3.2: Community participated in PHAST implementation | # community action plans updated after PHAST implementation # of community members participated in PHAST activities # of people reached by health/hyiene promotion activities | 2.3 Community members follow safer and healthier practices that reflect their increased knowledge and skills | % of people aware about safe disposal (seperating, recycle, composting, etc) of HH solid waster % of people aware about safe health and hygiene practices (e.g. handwashing) % of people with screens on windows to prevent mosquito entry
Hygiene Promotion Awareness (TT.E)
Objective 3
Construct HH latrines | 3.1.1 Targeted HH has a safe shelter with sanitation facilities | # HH provided core shelter with sanitation facilities | 3.1 Increased community capacity to manage its physical environment through infastructure and resources | % of community water and sanitation commiittees reguarly (in the last three months) collect fees in orfer to maintain facility from users % of facilities repaired by community water and sanitation committee with their resources | 3. Increase household and community access to safer and sustainable infastructure and resources
Water systems in Barangays | 3.2.1 Improved public infastructure in the taregted communities | # of community (public) facilities provided with improved (repaired or constructed) water and sanitation facilities | 3.2 Increased access to health services, safe water and reduce exposure to hazards within the baragay | % of water systems tested whose water quality meets the criteria per national standard
Drainage / Solid waste
WatSan in Health Unit / DCC
WatSan in Schools
Community led hazard mitigation projects (i.e. embankments, dyke, gabion-box walls, hillside stabilization, afforestation in river bank and coastal areas) based on the findings of participatory assessment (VCA)

## Data Analysis Assessment (hidden)
Tool | Purpose | Current Data Analysis | Analysis Completed by | Frequency | Follow up

## Data Flow (hidden)
Tool | Purpose | Collected by | Collection Frequency | To Supervisor | To PO
Summarizes and send to Heifer

## Follow Up Plan (hidden)
Tool | Task | Category | Responsibility | Status | Comments